Online Appendices

Online Table 1: Implementation indicators of DMHP by district at healthcare organisation, health facility, and community level

| Content of district mental healthcare plan | Anloga | Asunafo | Bongo | Total |
| --- | --- | --- | --- | --- |
| Healthcare organisation level |  |  |  |  |
| Leadership engagement & commitment | √ | √ | √ | √ |
| MoH has a budget for mental healthcare | √ | √ | √ | √ |
| Psychotropic medicine policy document in place | √ | √ | √ | √ |
| *Total amount of budget allocation for DMHP implementation | GHS 44,780.0 | GHS 80,000.0 | GHS 262581.0 |  |
| Health facility level |  |  |  |  |
| Provide mhGAP training for staff | 30 | 24 | 30 | 84 |
| Quarterly supervision of mhGAP trainees | 2 | 3 | 3 | 8 |
| Facilitate enrollment of service users on LEAP and NHIS | 73 | 0 | 150 | 223 |
| Provide services at the facility level | √ | √ | √ | √ |
| Raise awareness of mental health | √ | √ | √ | √ |
| Improve identification of mental health service users | √ | √ | √ | √ |
| Develop a proposal for funding for skills development |  | - | - | - |
| Community level |  |  |  |  |
| Train CHVs to identify and refer cases to health facilities | 30 | 26 | 31 | 87 |
| Number of quarterly radio programmes done | 3 | 2 | 7 | 12 |
| Improve mental health literacy through quarterly community durbars | 7 | 2 | 9 | 18 |
| Organise quarterly health talks in schools | 6 | 4 | 24 | 34 |
| Number of service users trained in livelihood support skills | 5 | 0 | 0 | 5 |
| Quarterly supervision of CHV activities by mental health coordinators | - | - | - | - |
| Home visits conducted | 147 | 110 | 661 | 918 |
| Health talks completed in communities | 66 | 72 | 255 | 393 |
| Outreach clinics conducted | 23 | 221 | 78 | 322 |
| Number of traditional and faith-based healing centres visited | 3 | 8 | 14 | 25 |
| Traditional and faith-based healers trained to identify and refer to health facilities | - | - | - | - |

Footnote:  Achieved= √, Not Achieved= - Number = done

*The budget was prepared and submitted but no funds were provided specifically for implementing the DMHP in any of the three districts.

Online Figure 1: Number of new cases per month from Jan 2021 – Jun 2023, Anloga District

Online Figure 2: Number of new cases per month from Jan 2021 – Jun 2023, Bongo District

Online Figure 3: Number of new cases per month from Jan 2021 – Jun 2023, Asunafo North District