## Arkusz1
Source | No. | SPM related Is article SPM related? | Source data in the literature | Problem category / AREA | Topics/prompts | DOI | Link | Title
Elsevier | 1 |  | All software engineers pointed out that the customer’s availability was important to detail the requirements, clarify doubts and validate the functionality, but his/her daily presence for this was not required. The customer should be available whenever the team needs. Due to the type of development, it was not necessary to have daily communication with the customer. The developers had little contact with the end user. The PO made the bridge with the customer. | Requirements Engineering, User Research | User involvement, user centered design | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Insufficient experience with ASD and with the activity of requirements specification affected the SRS’s content and how the requirements were described. | Requirements Engineering | Requirements management, documentation | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Some developers are also acting as a systems analyst. However, they do not yet have experience with the requirements specification activity, which compromises the quality of documentation.” The SRSs were based on use cases, mockups, business rules and NFRs. In spite of being more focused on the customer, as set out in the contract, these documents were not used to validate requirements | Requirements Engineering, Product knowledge management | Requirements management, documentation, unqualified people | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Inadequate management and prioritization of the requirements, | Requirement Engineering | Requirements management, prioritisation | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Bureaucratic practices applied to release, validate or certificate partial versions of the software, as well as to control changes in the requirements require an additional effort from the team. | Sofware Product Line / Software Development Life Cycle | Release cycle speed / Time-to-market | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Although software engineers had many years of experience with traditional software development, they had little experience with ASD. Many systems analysts had difficulty in defining what was relevant to include in the SRSs. Some rules descriptions had unnecessary details and redundant information, making it difficult to understand | Team | Unqualified people | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 1 |  | Despite the frequent software releases, the end users took a long time to validate them, causing problems in the requirements management. | Requirements Engineering, Software Product Line / Software Development Process | Release cycle speed / Time-to-market | 10.1016/j.jss.2018.04.064 | (http://www.sciencedirect.com/science/article/pii/S0164121218300888) | Quality of software requirements specification in agile projects: A cross-case analysis of six companies
Elsevier | 2 |  | Domain analysts, product managers, or customers aim to capture the important features and differences among a set of related products. A case-by-case reviewing of each product description is a laborious and time-consuming task that fails to deliver a condense view of a family of product. | Product Knowledge Management | Product description, sharing knowledge | 10.1016/j.jss.2016.11.018 | (http://www.sciencedirect.com/science/article/pii/S0164121216302242) | Automated extraction of product comparison matrices from informal product descriptions
Elsevier | 3 |  | Company K substitutes a partner and stops sharing business deals if the partner may damage the image of the product due to quality issues | Software Product Line / Software Development process | Software Quality | 10.1016/j.jss.2018.07.036 | (http://www.sciencedirect.com/science/article/pii/S0164121218301468) | Strategies for managing power relationships in software ecosystems
Elsevier | 3 |  | During the process of establishing a new software ecosystem, SMEs are seeking for new resources to increase business opportunities and access different consumer markets. | Organisational - strategic | Partnership management | 10.1016/j.jss.2018.07.036 | (http://www.sciencedirect.com/science/article/pii/S0164121218301468) | Strategies for managing power relationships in software ecosystems
Elsevier | 4 |  | Still, in many cases it is hard to find adequately trained people and sufficiently integrated development tools for complex solutions, especially in the case of small and medium sized enterprises. | Team, Organisational - operational | Tools, Unqualified people | 10.1016/j.procir.2017.03.013 | (http://www.sciencedirect.com/science/article/pii/S2212827117301579) | Integrating Requirements Engineering for Different Domains in System Development – Lessons Learnt from Industrial SME Cases
Elsevier | 4 |  | Additionally, rapid technological changes combined with a highly competitive market have induced a need for e.g. implementing new processes and production methods for reducing “time to market” waste and failures, as well as in order to be both appropriate in terms of quality and cost effective [4] and meet the customers’ expectation | Software product line/ Software Development Life Cycle | Release cycle speed / time - to market, software quality, price management | 10.1016/j.procir.2017.03.013 | (http://www.sciencedirect.com/science/article/pii/S2212827117301579) | Integrating Requirements Engineering for Different Domains in System Development – Lessons Learnt from Industrial SME Cases
Elsevier | 5 |  | Processes: Long processers or too long to do it; Autosar (a process tool); Useless reporting (as part of processes) | Software product line/ Software Development Life Cycle | Release cycle speed / time - to market, software quality | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Esevier | 5 |  | Requirements and Design: Developing wrong requirements, change in the roadmap, not-well dfined req for design team, heavy useless architecture | Requirements Engineering, Software Product Line / Software Development Process | Requirements management, prioritatization, system architecture | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Management and Organizational aspects: Lack of Trust and request for monitoring every thing; lots of meetings/presentations; non-homogeneous ways of working; formal-approval or different phrases | Organisational - strategic, Organisational - operational | Trust, desicion making process | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | No/or hard access to customer info w.r.t. feature usage; no access to hardware "we discover things late" | User research, Requirements Engineering | User centered design, customer feedback, user involvement | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Pre-studies & Proof of concept which doesn't lead to development; predevelopment activities/stuies; activities that do not make it to release such as systematization and analisys | User research | prioritisation, continous experimentation | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Third party, External suppliers (not easy to communicate or ask/force them to deliver what we need | Organisational - strategic | Partnership management | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Partially-done-work | Organisational - operational, Requirements Engineering | Agile, documentation | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Trouble-reports | Software Product Line/ Software Development Process | Software quality | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Re-works - re-inventting the wheel; no common design patterns | Organisational - operational | Continous Experimentation | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 5 |  | Right feature but late; late to market-window | Software Product Line/ Software Development Process | Time-to-market | 10.1016/j.infsof.2018.08.006 | (http://www.sciencedirect.com/science/article/pii/S095058491830171X) | An exploratory study of waste in software development organizations using agile or lean approaches: A multiple case study at 14 organizations
Elsevier | 6 |  | there are often two major problems during requirement gathering. First, there are communication and collaboration differences and gaps between customers and teams. Second, unstandardized RE practices are used. | Requirements Engineering, Team | requirements management, user involvement, communication | 10.1016/j.jss.2018.08.059 | (http://www.sciencedirect.com/science/article/pii/S0164121218301729) | An anatomy of requirements engineering in software startups using multi-vocal literature and case survey
Elsevier | 6 |  | some startups consider business as needed to create requirements and solutions, and they do not focus on users’ problems. | Requirement Engineering, User Research | user involvement, user centered design, customer feedback | 10.1016/j.jss.2018.08.059 | (http://www.sciencedirect.com/science/article/pii/S0164121218301729) | An anatomy of requirements engineering in software startups using multi-vocal literature and case survey
Elsevier | 7 | TRUE | In both of the companies, reaching end users to be involved in the experiment was found to be challenging. | Requirements engineering | user involvement | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 | TRUE | There was a multi-layered structure of stakeholders in both cases. Although this is expected, especially in large software organizations and multi-sided business models, it was a challenge to isolate and identify which stakeholders should be involved in the experiments and whose value the experiments should fulfil. | Organisational, User research | stakeholders management, customer feedback, continous experimentation, responsibilities | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 | TRUE | Inexperience with experimentation Although the aim of the introduction process was to give knowledge to the companies, the fact that they had not conducted structured experiments before resulted in some hesitancy and indecisiveness in attempting to make experiment-related decisions. For instance, in the case of company B, one of the reasons for not involving real users in the experiment was due to lack of confidence and wanting to wait until more experience had been gained. | User research | user involvement, decision making process | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 | TRUE | In both cases it was difficult to access both earlier implementations of the companies’ services. This prevented the teams from forming hypotheses based on comparison or base data. Also, lack of such data made defining success criteria challenging as there was no comparison point. | Software development process | documentation, data collection | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 | TRUE | Existing and short deadlines. Related to the third challenge of experimenting on an evolving product or service, when a company starts doing experimentation, they have to work with or around existing deadlines and commitments which naturally affect experiment prioritization. This was observed in both Company A and Company B. | Organisational - operational | prioritization, time, continous experimentation | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 | TRUE | Length of the process. The introduction process took a relatively long time as it was a study that had elements of action research. For instance, the process from understanding context to running first structured experiment took 11 months for Company A and 3 months for Company B. This unfortunately might affect the motivation and persistence of the company participants. | Organisational - operational | time | 10.1016/j.jss.2017.07.009 | (http://www.sciencedirect.com/science/article/pii/S0164121217301474) | Introducing continuous experimentation in large software-intensive product and service organisations
Elsevier | 7 |  | Both of the companies were in the middle of developing a product and service that was evolving from an old solution to a new, modern solution. Thus, when selecting the first experiment to run, care had to be taken not to create any conflicts between completed, current, and planned development, which can take some time and effort to coordinate. | Organisational - operational | time | 10.1016/j.infsof.2016.12.005 | (http://www.sciencedirect.com/science/article/pii/S0950584916304815) | A risk management framework for distributed agile projects
Elsevier | 8 |  | Problem with scaling continous integration. Prominent among these is the issue of scalability: continuous integration has been reported to be possible to scale, but with difficulties. | Software product line/ Software Development Life Cycle | continuous integration | 10.1016/j.jss.2017.02.003 | (http://www.sciencedirect.com/science/article/pii/S0164121217300328) | The continuity of continuous integration: Correlations and consequences
Elsevier | 8 |  | There is evidence that the size of the organization influences ways of working, which in turn correlate with the degree of continuity, raising the question of software manufacturability. | Software product line/ Software Development Life Cycle, Organisational - operational | Release cycle speed / time-to-market | 10.1016/j.jss.2017.02.003 | (http://www.sciencedirect.com/science/article/pii/S0164121217300328) | The continuity of continuous integration: Correlations and consequences
Elsevier | 9 |  | Time to market‘release early, release often. The solution to this is, of course, to shorten the time between the key idea that a startup tries to market, and the delivery to its customers. | Software Product Line | Release cycle speed / time-to-market | 10.1016/j.jss.2015.06.063 | (http://www.sciencedirect.com/science/article/pii/S0164121215001430) | Continuous software engineering: A roadmap and agenda
Elsevier | 9 |  | In other words, an understanding of what constitutes ‘value’ to the customer is unclear. Informed by the principles of lean manufacturing, lean startups attempt to solve this problem by continuous learning through a process of experimentation (as discussed in more detail below). | Organisational - operational | Continous Experimentation | 10.1016/j.jss.2015.06.063 | (http://www.sciencedirect.com/science/article/pii/S0164121215001430) | Continuous software engineering: A roadmap and agenda
Elsevier | 9 |  | The disconnect between software developers and business managers is an old and often cited problem. | Team | Communication | 10.1016/j.jss.2015.06.063 | (http://www.sciencedirect.com/science/article/pii/S0164121215001430) | Continuous software engineering: A roadmap and agenda
Elsevier | 9 |  | The central problem is captured in the apocryphal, but very apt quote from the business manager, who described the key problem with his company’s flagship software product, as being that he knew that half of the features being offered were not used by any customers, but the trouble was that he did not know which half | User research | user bahavioral data, business intelligence | 10.1016/j.jss.2015.06.063 | (http://www.sciencedirect.com/science/article/pii/S0164121215001430) | Continuous software engineering: A roadmap and agenda
Elsevier | 10 |  | The main problem related to the Industrie 4.0 paradigm implementation in these companies lies in the lack of the awareness of the link between business and technological worlds on the strategic and tactical levels within the company, as well as the failure to meet the production needs [4] [5]. In reality, many companies are treating digital transformation projects as typical IT projects. In fact, there is a basic challenge of understanding the drivers behind Industrie 4.0 and digital transformation within the organization. | Organisational - strategic | Strategy | 10.1016/j.procir.2018.03.151 | (http://www.sciencedirect.com/science/article/pii/S2212827118303081) | Industrie 4.0 roadmap: Framework for digital transformation based on the concepts of capability maturity and alignment
Elsevier | 11 |  | [all in C5] customer data preservation, documentation, feature discovery, marketing, more deployed bugs, third party integration, users do not like updates, deployment downtime [C25c(*)] | Software development process | software quality, documentation | 10.1016/j.infsof.2016.10.001 | (http://www.sciencedirect.com/science/article/pii/S0950584916302324) | Problems; causes and solutions when adopting continuous delivery—A systematic literature review
Elsevier | 11 |  | The proposed benefits of CD are increased visibility, faster feedback and empowerment of stakeholders [1]. | User research | customer feedback, stakeholders management | 10.1016/j.infsof.2016.10.001 | (http://www.sciencedirect.com/science/article/pii/S0950584916302324) | Problems; causes and solutions when adopting continuous delivery—A systematic literature review
Elsevier | 11 |  | Increased technical debt [6], lower reliability and test coverage [6], lower customer satisfaction [6], [7], time pressure [6], transforming towards CD [7], increased QA effort [7], applying CD in the embedded domain [7]. | User research, Software develpment process | technical debt, user centered design, continuous integration, software quality | 10.1016/j.infsof.2016.10.001 | (http://www.sciencedirect.com/science/article/pii/S0950584916302324) | Problems; causes and solutions when adopting continuous delivery—A systematic literature review
Elsevier | 12 |  | On the other hand, the 40-hour week practice can be problematic from a scheduling perspective as it tries to control overtime work, and the On-site customer can represent an unwanted time pressure element and it may increase requirements volatility. | Requirements engineering | time, requirements management | 10.1016/j.infsof.2017.11.015 | (http://www.sciencedirect.com/science/article/pii/S0950584917305098) | Technical debt and agile software development practices and processes: An industry practitioner survey
Elsevier | 12 |  | Industry practitioners perceive concrete technical debt to be difficult to identify, suggesting that it is complicated to manage. | Software development process | technical debt | 10.1016/j.infsof.2017.11.015 | (http://www.sciencedirect.com/science/article/pii/S0950584917305098) | Technical debt and agile software development practices and processes: An industry practitioner survey
Elsevier | 13 |  | Creating temporary solutions to the code base increases complexity, which makes further development hard and time-consuming. The list contains TD “items”, each of which represents an incomplete task that may cause problems in the future. | Software development process | technical debt | 10.1016/j.jss.2016.05.018 | (http://www.sciencedirect.com/science/article/pii/S016412121630053X) | How do software development teams manage technical debt? – An empirical study
Elsevier | 13 |  | TD communication was structured well in the development team. The team manager had wide technical knowledge, which helped TD communication between the management and the developers. This also helped the development team in situations where the business stakeholders gave impossible deadlines to work with, because the team manager would explain the issues of possible TD to the business management. However, the development team expressed a problem in communication, as the development of new features was always prioritized the highest, and the code base improvements were not done before them. | Software development process, Requirements engineering, Team | technical debt, communication, time, prioritisation | 10.1016/j.jss.2016.05.018 | (http://www.sciencedirect.com/science/article/pii/S016412121630053X) | How do software development teams manage technical debt? – An empirical study
Elsevier | 13 |  | TD repayment was not done in any organized process. One of the software architects mentioned that in the current process, the repayment of a TD issue was usually started only when the issue started to be highly problematic for the development team to handle and there was no other way than just to refactor, rewrite or redesign it. If a developer noticed a need for refactoring, it was often taken care of by the developer, without any actual systematic repayment process. | Software development process | technical debt | 10.1016/j.jss.2016.05.018 | (http://www.sciencedirect.com/science/article/pii/S016412121630053X) | How do software development teams manage technical debt? – An empirical study
Elsevier | 14 | TRUE | Limited resources were a highly recurrent theme in the interviews. There was a lack of time and funding to invest in experimentation. On the other hand, some interviewees emphasized the potential long-term benefits of investing in experimentation. | Organisational - operational | time, budget, continous experimentation | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 14 | TRUE | Identifying the metrics to evaluate created customer value and product success was a major challenge both in relation to dedicated experiments and to the general observation of product usage. We measure the wrong things for some of [the] products.'' | Software development process | data collection | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 15 | TRUE | Concern over slow release cycles was one of the central themes in terms of product management | Software development process | release cycle speed / time-to-market | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 15 | TRUE | Half of the company representatives considered organizational culture a major obstacle to moving towards an experimental mode of operation. | Organisational - strategic | trust in team, decistion making process, continous experimentation | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 15 | TRUE | Interviewees also expressed concern over deficiencies in the analysis of collected customer feedback and other data. Lack of time and analytic expertise emerged as possible reasons for inadequate data analysis. | Software development process | customer feedback, data colection | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 15 | TRUE | A further set of issues was related to defining the product roadmap. Identifying a truly viable MVP was considered “very easy to say, very hard to do.` | Requirements engineering | product roadmap | 10.1016/j.infsof.2016.04.008 | (http://www.sciencedirect.com/science/article/pii/S0950584916300647) | Raising the odds of success: the current state of experimentation in product development
Elsevier | 16 |  | Some important tasks such as selecting and prioritization requirements can be an extremely arduous and exhaustive task throughout the process, depending on the size of the software features of the application domain and interdependence between requirements, among others factors. | Requirements Engineering | prioitization, requirements management | 10.1016/j.jss.2014.09.038 | (http://www.sciencedirect.com/science/article/pii/S0164121214002118) | Software requirements selection and prioritization using SBSE approaches: A systematic review and mapping of the literature
Elsevier | 17 |  | Many of the software product companies are constantly facing the challenge of adjusting their problem-solving approaches to fit with the changing nature of the problem to be solved. | User research | user centered design | 10.1016/j.jss.2014.03.050 | (http://www.sciencedirect.com/science/article/pii/S0164121214000776) | Using a grounded theory approach for exploring software product management challenges
Elsevier | 17 |  | As the software product organization's design problem has evolved to be more difficult to comprehend, the tools, techniques and methods belonging to the expert paradigm have begun to lose their effectiveness. Yet, many software product development organizations have been tempted to hold on to the actions that were once successful. Thus, in the time of a paradigm shift, research and practice have, to a certain extent, suffered from paradigm paralysis. Requirements elicitation crises and requirements prioritization crises are symptoms of such paradigm paralysis. | Requirements engineering | requirements management, prioritization | 10.1016/j.jss.2014.03.050 | (http://www.sciencedirect.com/science/article/pii/S0164121214000776) | Using a grounded theory approach for exploring software product management challenges
Elsevier | 17 |  | The inadequate fit between the nature of the design problem and the problem solving approach continues to increase until the beliefs and assumptions of the expert paradigm are questioned and a new paradigm is adopted. | User research / Product discovery | user centered design | 10.1016/j.jss.2014.03.050 | (http://www.sciencedirect.com/science/article/pii/S0164121214000776) | Using a grounded theory approach for exploring software product management challenges
Elsevier | 18 |  | Prior research finds that agile teams can face ownership and implementation obstacles to making decisions.This current research contributes to these findings by stating agile teams must make decisions in support of Team Satisfaction, which can combat against the ownership and implementation decision obstacles. | Organisational - opperational | decision making process | 10.1016/j.infsof.2013.11.003 | (http://www.sciencedirect.com/science/article/pii/S0950584913002176) | Performance on agile teams: Relating iteration objectives and critical decisions to project management success factors
Elsevier | 19 | TRUE | Generally speaking, all we do is not mandatory for engineering. It is rather a recommendation than a command. As far as I understand, this is a typical problem of product management in most organizations… The product manager is a person who can influence what happens only by persuasion and motivation. | Organisational - operational | responsibilities | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | The most important point here is that the responsibility and the authority are not shared between people. This is the worst thing that can happen in a software company, in any company.— | Organisational - strategic, Organisational - operational | responsibilities, trust in team | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | The product managers from the large organizations (Organizations A, C and D) described problems related to their position in the corporate hierarchy. Overall, these problems formed two different problem domains. The first domain included the problems they had in collaboration with other departments including marketing, sales, and development departments. | Requirements engineering, Organisational - operational | responsibilities, stakeholders management | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | The second domain consisted of the problems related to making strategic and tactical decisions about a particular product without permission from the higher management. In some cases decision making was considered as the main characteristic of a product manager. If the product manager is not able to make decisions then he is not a product manager. | Organisational - operational | decision making process | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | The product managers with limited authority usually were responsible for technical roadmapping and features prioritization while product managers who had higher level of authority were usually responsible for making strategic decisions related to the product vision and strategy. | Organisational - operational, Requirements engineering | decision making process, product roadmap, prioritisation, strategy | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | for example, as a product manager I get an idea about our product but I do not know how many people are interested in that. I go to the analysts and ask them to research the area and determine which features are necessary for our users and how many people are interested in our product. Our headquarter office is engaged in the distribution of budgets and people. I do not have influence on managing resources because our office has no influence on this at all. The resource management was especially a problem for medium-size companies, where product managers had very limited access to any resources. | User research, Organisational - operational, Team | responsibilities, stakeholders management | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 19 | TRUE | We observed cases where the product manager was responsible for the communication function only. He or she was a facilitator between all departments including marketing, development, sales, and support, and was responsible for taking part in solving their problems. His role was to be an intermediate link for the top management level and to solve emerging problems without top management involvement. | Organisational - operational | responsibilities | 10.1016/j.jss.2013.07.045 | (http://www.sciencedirect.com/science/article/pii/S0164121213001891) | What are the roles of software product managers? An empirical investigation
Elsevier | 20 | TRUE | Dysfunctional organization with unclear responsibilities and silo work which results in continuously changing focus and schedules | Organisational - operational | responsibilities | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | The problem is not so much that stakeholders are not known, however that the interdependencies, roles and expectations to requirements are unclear. It is easier to talk to engineers in identifying requirements than to trace needs from various groups to concrete technical requirements. | Requirements engineering | stakeholders management | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | While several requirement selection factors are covered in the different models, most methods fail to address factors such as stakeholder value or internal value. We found in our empirical study a similar result with respect to specifying value dimensions and getting sustainable stakeholder commitments. | Requirements engineering | stakeholders management | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | A number of challenging issues were found, including communication gaps between marketing and development, selecting the right level of process support, basing the release plan on uncertain estimates, and managing the constant flow of requirements. | Requirements engineering, Team | communication, requirements management | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | In reality however, only 33% are actively implementing this vision. This means that about half share the concept of a strong product manager. For the other half, product managers are mostly subordinate to marketing and play an administrative role, such as maintaining technical roadmaps. | Organisational - operational | responsibilities | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | These product managers do not master their role. Insufficient requirements engineering is typically the first sign of product management failure. Even as they try to specify requirements, they are not developing requirements with other stakeholders. | Requirements engineering | stakeholders management, requirements management | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | There seems to be in many companies a vicious circle of insufficient competences and in consequence a weak perception of the role and its incumbents by senior management, which in turn would not strengthen the role. | Organisational - operational | responsibilities, unqualified people | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | The difficulties with misunderstanding needs, changing and creeping requirements, missed deadlines and budgetary commitments and failing business opportunities can only be cured with a thorough understanding and implementation of the product manager's role. | Requirements engineering, Organisational - operational | requirements management, time | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | No standardized processes across the company with a slow and cumbersome decision-making process and many individual ad-hoc agreements. | Organisational - operational | responsibilities, decision making process | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | Insufficient requirements which are often just collections of what had been heard at customer visits and other such events, but not mapped to value creation and business cases. | Requirements engineering | requirements management | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Elsevier | 20 | TRUE | Lack of strategy and unclear strategy and roadmaps with unclear dependencies and fuzzy technical requirements and impacts. | Requirements Engineering, Organisational - strategic | strategy, product roadmap | 10.1016/j.jss.2013.12.042 | (http://www.sciencedirect.com/science/article/pii/S0164121214000156) | Software product management – An industry evaluation
Scopus | 21 |  | Inconsistent subjective quality measurement | Software product line / software product development process | Software quality | 10.1007/978-3-319-91446-6_28 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85048062230&doi=10.1007%2f978-3-319-91446-6_28&partnerID=40&md5=845396a047319d90b7609c7adb8b0761 | Consistency-driven pairwise comparisons approach to software product management and quality measurement
Scopus | 22 |  | none |  |  | 10.1109/EMR.2018.2810099 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85045543893&doi=10.1109%2fEMR.2018.2810099&partnerID=40&md5=c942353fbb2d9c640883e535ae6c0999 | Data driven product management
Scopus | 23 |  | Many large organizations are struggling to successfully adopt agile methods | Organisational - operational | agile | 10.1007/s10664-016-9491-z | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85009188417&doi=10.1007%2fs10664-016-9491-z&partnerID=40&md5=416b03be9a0e50212ddefdd4cfd86b3a | Managing the requirements flow from strategy to release in large-scale agile development: a case study at Ericsson
Scopus | 23 |  | Due to the short history of agile methods use in large organizations, reports on the best practices of agile development in large organizations are lacking and many large organizations are struggling to implement efficient requirements processes. Efficient requirement process hard to be achieved | Organisational - operational, Requirements Engineering | agile, requirements | 10.1007/s10664-016-9491-z | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85009188417&doi=10.1007%2fs10664-016-9491-z&partnerID=40&md5=416b03be9a0e50212ddefdd4cfd86b3a | Managing the requirements flow from strategy to release in large-scale agile development: a case study at Ericsson
Scopus | 23 |  | Agile RE is claimed to decrease process overheads1 due to the smaller amount of required requirements and system documentation. Lack of requirements and system documentation | Organisational - operational, Requirements Engineering, Product Knowledge management | agile, requirements | 10.1007/s10664-016-9491-z | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85009188417&doi=10.1007%2fs10664-016-9491-z&partnerID=40&md5=416b03be9a0e50212ddefdd4cfd86b3a | Managing the requirements flow from strategy to release in large-scale agile development: a case study at Ericsson
Scopus | 23 |  | Agile RE relies on the availability of the customers, but due to cost, time and trust issues the access to the customers or customer representatives is often limited | User research | Customer involvement, customer feedback, user centered seign | 10.1007/s10664-016-9491-z | https://www.scopus.com/inward/record.uri?eid=2-s2.0-85009188417&doi=10.1007%2fs10664-016-9491-z&partnerID=40&md5=416b03be9a0e50212ddefdd4cfd86b3a | Managing the requirements flow from strategy to release in large-scale agile development: a case study at Ericsson
Scopus | 24 |  | The Solution Architect APO was a representative of the product management organization [...]. All System Architect APOs were located in Finland, as well as most of the Solution Architect APO. In Greece, a couple of Solution Architect APOs were recently transferred to this project. Thus, the APOs had to communicate through teleconferencing with the teams located at other sites. | Organisational - operational, Resources | Distributed teams | 10.1109/ICGSE.2016.34 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84994609189&doi=10.1109%2fICGSE.2016.34&partnerID=40&md5=2bbcd316cd5bf0a2ea3361308848257a | Scaling scrum in a large globally distributed organization: A case study
Scopus | 25 | TRUE | One participant described the role as a combination of a diplomat adviser and juggler because there are a lot of voices with different needs and the Product Owner needs to communicate with all of them. | Requirements Engineering | stakeholder management | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 25 | TRUE | One participant said that the Product Owner role is challenging because even though the team is responsible for their delivery the Product Owner is in the forefront of that, the one seeing to that the delivery happens and it is compatible to what was initially planned | Organisational - operational | responsibilities | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 25 | TRUE | Every Product Owner found it extremely important to spend time with the team every day, as much as they physically could to but some struggled with that as they worked with more than one team and had to attend to various meetings. | Organisational - operational | time | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 25 | TRUE | The challenge is also that the Product Owner has to be an indirect leader of the team, he has some authority to make decisions for the team but he very rarely wants to act on that authority and be the only one making decisions that affect the whole team and their work | Organisational - operational | decision making process, responsibilities | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 25 | TRUE | Most of the Product Owners talked about the stakeholder side as being one of the most challenging parts of their role. It is difficult to motivate a team that does not know for whom it is working and lacks a purpose. One participant said that his biggest challenge was to sell his vision of the development to the developers on his team | Requirements Engineering | stakeholder management | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 25 | TRUE | Communication was also mentioned as being one of the Product Owners’ main challenge | Team | communication | 10.1007/978-3-319-44902-9_1 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84986222611&doi=10.1007%2f978-3-319-44902-9_1&partnerID=40&md5=11c459011ac5341e4ebaeee1b1773a14 | Responsibilities and challenges of product owners at Spotify - an exploratory case study
Scopus | 26 |  | Implementing and managing the consequences of design change in the context of complex products is challenging. Design changes generate significant volumes of information and product management is becoming increasingly information intensive. | User research | product design | 10.1007/978-3-319-32098-4_21 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84966549605&doi=10.1007%2f978-3-319-32098-4_21&partnerID=40&md5=95a9be629523bced70f4776c840193bd | Product change management and future information architectures
Scopus | 27 |  | For both projects, the main problem of managing TD may be divided into the following parts: debt identification and visualization, measurement effort for payment and decision making of when and which items should be payed off. The Product Owner role in both companies understood the importance of Technical Debt monitoring and prioritization during a development cycle. | Software product line/Software development process | technical debt | 10.1109/Agile.2015.7 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84962124100&doi=10.1109%2fAgile.2015.7&partnerID=40&md5=3acb74b43b01109410b079ff5800e336 | Managing Technical Debt in Software Projects Using Scrum: An Action Research
Scopus | 28 |  | (1) The requirements/architecture alignment problem for software products is inherently differentthan the same problem for tailor-made software; | Software product line/Software development process | system architecture | 10.1109/TwinPeaks.2015.13 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954543681&doi=10.1109%2fTwinPeaks.2015.13&partnerID=40&md5=9850b2bd59153221895a6581b4ff967a | Bridging the Twin Peaks-The Case of the Software Industry
Scopus | 28 |  | (2) bridgingthe Twin Peaks corresponds to deﬁning and enacting a stepwise evolution of the product architecture; | Software product line/Software development process | system architecture | 10.1109/TwinPeaks.2015.13 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954543681&doi=10.1109%2fTwinPeaks.2015.13&partnerID=40&md5=9850b2bd59153221895a6581b4ff967a | Bridging the Twin Peaks-The Case of the Software Industry
Scopus | 28 |  | (3) communication tasks are ascribed to the product manager rather than the architect | Team | communication | 10.1109/TwinPeaks.2015.13 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954543681&doi=10.1109%2fTwinPeaks.2015.13&partnerID=40&md5=9850b2bd59153221895a6581b4ff967a | Bridging the Twin Peaks-The Case of the Software Industry
Scopus | 28 |  | (4) integrated and cross-disciplinary tools are key to main-tain requirements/architecture alignment. | Organisational-operational | tools | 10.1109/TwinPeaks.2015.13 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954543681&doi=10.1109%2fTwinPeaks.2015.13&partnerID=40&md5=9850b2bd59153221895a6581b4ff967a | Bridging the Twin Peaks-The Case of the Software Industry
Scopus | 29 |  | A fundamentally different approach to deciding what to build is required: requirements should be treated as hypothesis throughout the development process and constant feedback from users and systems in the field should be collected to dynamically reprioritize and change requirements. | Requirements engineering, User research | requirements management, continuout experimentation | 10.1109/TwinPeaks.2015.8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954571184&doi=10.1109%2fTwinPeaks.2015.8&partnerID=40&md5=a323cba00a57d8630f3ff80fe729e7ec | Architecting to Ensure Requirement Relevance: Keynote TwinPeaks Workshop
Scopus | 29 |  | This requires architectural support beyond the current state of practice as continuous deployment, split testing and data collection need to be an integral part of the architecture. | Software product line/Software development process | system architecture, split testing | 10.1109/TwinPeaks.2015.8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84954571184&doi=10.1109%2fTwinPeaks.2015.8&partnerID=40&md5=a323cba00a57d8630f3ff80fe729e7ec | Architecting to Ensure Requirement Relevance: Keynote TwinPeaks Workshop
Scopus | 30 |  | the lack of collaboration between the customers and software development teams causes such failures. | User research | customer feedback | 10.1007/978-3-319-18612-2_8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84942814499&doi=10.1007%2f978-3-319-18612-2_8&partnerID=40&md5=2f821cea4b8a6eebae3de8aa250cd9f8 | Why the development outcome does not meet the product owners’ expectations?
Scopus | 30 |  | the POs had diffi-culties communicating and prioritizing the requirements to the development teams because the requirements were not clear for the POs themselves | Team, Requirements enginnering | communication, prioritization | 10.1007/978-3-319-18612-2_8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84942814499&doi=10.1007%2f978-3-319-18612-2_8&partnerID=40&md5=2f821cea4b8a6eebae3de8aa250cd9f8 | Why the development outcome does not meet the product owners’ expectations?
Scopus | 30 |  | This was caused by the lack of PO resources and the use of third parties in eliciting and defining the re-quirements. | Organisational-operational | agile, time, budget | 10.1007/978-3-319-18612-2_8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84942814499&doi=10.1007%2f978-3-319-18612-2_8&partnerID=40&md5=2f821cea4b8a6eebae3de8aa250cd9f8 | Why the development outcome does not meet the product owners’ expectations?
Scopus | 30 |  | The geographical distance, language barriers, and inactive software de-velopers exacerbated the problems. | Organisational-operational | distributed teams | 10.1007/978-3-319-18612-2_8 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84942814499&doi=10.1007%2f978-3-319-18612-2_8&partnerID=40&md5=2f821cea4b8a6eebae3de8aa250cd9f8 | Why the development outcome does not meet the product owners’ expectations?
Scopus | 31 |  | Product management often finds it difficult to get timely and accurate feedback from customers | User research | customer feedback | 10.1007/978-3-319-19593-3_12 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84937459077&doi=10.1007%2f978-3-319-19593-3_12&partnerID=40&md5=f31d9821fb6faa40b83cce43c9d7a106 | Customer feedback and data collection techniques in software R&D: A literature review
Scopus | 31 |  | In previous research, we coined the term the ‘open loop’ problem, referring to the challenges for product management to receiveaccurate customer feedback to use as a basis in their decision-making processes | Organisational-operational | decision-making process | 10.1007/978-3-319-19593-3_12 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84937459077&doi=10.1007%2f978-3-319-19593-3_12&partnerID=40&md5=f31d9821fb6faa40b83cce43c9d7a106 | Customer feedback and data collection techniques in software R&D: A literature review
Scopus | 31 |  | despite that significantdata is being collected, companies have insufficient knowledge about how their products are used and what features the customers actually appreciate and desire to use in the future | User research | user behavioral data | 10.1007/978-3-319-19593-3_12 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84937459077&doi=10.1007%2f978-3-319-19593-3_12&partnerID=40&md5=f31d9821fb6faa40b83cce43c9d7a106 | Customer feedback and data collection techniques in software R&D: A literature review
Scopus | 31 |  | there is typically a weak link between customer data and product management decisions, and no accurate way in which the organizations can assess whether the features that were prioritized during the road mapping process are also the features that are appreciated and used by customers and that generate revenue to the company | Requirements engineering | prioritization, product roadmap | 10.1007/978-3-319-19593-3_12 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84937459077&doi=10.1007%2f978-3-319-19593-3_12&partnerID=40&md5=f31d9821fb6faa40b83cce43c9d7a106 | Customer feedback and data collection techniques in software R&D: A literature review
Scopus | 32 | TRUE | Comparison of the two knowledge maps revealed three main themes (requirements gathering, customer collaboration, and decision making) in the gathered data along with several sub-themes. | Requirements engineering | user involvement, decison making process | 10.1007/978-3-642-37422-7_28 | https://www.scopus.com/inward/record.uri?eid=2-s2.0-84875855010&doi=10.1007%2f978-3-642-37422-7_28&partnerID=40&md5=d07e9d905c47a7f4e1420ef34a55a173 | Adjusting to increasing product management problems: Challenges and improvement proposals in one software company
SpringerLink | 33 | TRUE | The trouble with linking business strategy to solution planning. The business strategy did not provide clear guidance regarding how to define the target customer at a given time and how to elicit, analyze, and prioritize the corresponding requirements. In both case study organizations, key customers’ urgent needs and the pressure of short-term sales had overrun long-term plans on several occasions. | Requirements engineering | strategy, proritisation, requirements engingeering | 10.1007/s00766-013-0186-3 | http://link.springer.com/article/10.1007/s00766-013-0186-3 | Roadmapping problems in practice: value creation from the perspective of the customers
SpringerLink | 33 | TRUE | Disadvantage of a feature-driven mind-set. Long-term planning in both companies was driven by the prioritization of software features. The solution-planning processes had been software component focused. | Requirements engineering | prioritisation | 10.1007/s00766-013-0186-3 | http://link.springer.com/article/10.1007/s00766-013-0186-3 | Roadmapping problems in practice: value creation from the perspective of the customers
SpringerLink | 33 | TRUE | Customer activities and services lacked the same degree of attention. Both companies identified the challenge of emphasizing the analysis of customer’s processes and how the markets change over time, as well as planning for the business goals of the products. | User research, requirements engineering | user involvement, user centered design, customer feedback, business intelligence | 10.1007/s00766-013-0186-3 | http://link.springer.com/article/10.1007/s00766-013-0186-3 | Roadmapping problems in practice: value creation from the perspective of the customers
SpringerLink | 33 | TRUE | Difficulty of defining and commercializing services. Here, a solution refers to a bundle of service and product components. Product components refer to software that can be a software platform, portal, or application. An example of a product component is a mass calculation application that allows Tekla’s customer to estimate the amount of soil materials needed in construction. Service component refers to a customer’s activity in which the company has a significant role. An example of a service component is marketing support, in which F-Secure develops marketing material and campaigns together with the operators. However, distinguishing between product and solution components is not always evident. New service development within software product development was perceived as challenging. The practitioners felt that the history of developing software components has hindered their ability to understand the customer needs related to services. | Organisational - strategic, Organisational - operational | responsibilities, business model | 10.1007/s00766-013-0186-3 | http://link.springer.com/article/10.1007/s00766-013-0186-3 | Roadmapping problems in practice: value creation from the perspective of the customers
SpringerLink | 33 | TRUE | Challenge of fragmented customer knowledge The case study companies faced challenges in terms of sharing customer knowledge between key personnel. Customer knowledge in both companies was fragmented, which meant that different employees were knowledgeable about different areas of their customers’ activities. The study found that only a few employees had a good understanding of their customers’ activities. Units other than product and R&D management had difficulty participating in and affecting solution planning. The role of other functions, such as marketing, sales, support, and documentation, seemed to be overlooked in discussions about future plans. Therefore, members of other units found it difficult to get their ideas heard. | Product knowledge management | Product description, sharing knowledge | 10.1007/s00766-013-0186-3 | http://link.springer.com/article/10.1007/s00766-013-0186-3 | Roadmapping problems in practice: value creation from the perspective of the customers
WebOfScience | 34 | TRUE | An attempt to make radical rather than incremental changes has been identified as a common problem in the adoption of product management [16]. Some studies also warn about the introduction of disruptive changes [17], [18] | Organisational - operational |  | 10.1108/JAMR-03-2016-0022 | http://han.bg.pg.edu.pl/han/web-of-science/apps.webofknowledge.com/full_record.do?product=WOS&search_mode=GeneralSearch&qid=2&SID=E2GDNEgElWSeeR852w7&page=3&doc=22&cacheurlFromRightClick=no | Core software product management activities
WebOfScience | 34 | TRUE | Since companies face common problems in the adoption of SPM like long release cycles, short-term thinking, and a lack of constant collaboration between organizations and customers [16], | Software development process, User research | release cycle speed, user centered design | 10.1108/JAMR-03-2016-0022 | http://han.bg.pg.edu.pl/han/web-of-science/apps.webofknowledge.com/full_record.do?product=WOS&search_mode=GeneralSearch&qid=2&SID=E2GDNEgElWSeeR852w7&page=3&doc=22&cacheurlFromRightClick=no | Core software product management activities
WebOfScience | 34 | TRUE | An attempt to adopt all SPM activities instantly has been identified as a common problem in product management | Organisational - operational | responsibilities | 10.1108/JAMR-03-2016-0022 | http://han.bg.pg.edu.pl/han/web-of-science/apps.webofknowledge.com/full_record.do?product=WOS&search_mode=GeneralSearch&qid=2&SID=E2GDNEgElWSeeR852w7&page=3&doc=22&cacheurlFromRightClick=no | Core software product management activities
WebOfScience | 35 | TRUE | So far, planning decisions were based on stakeholder opinion and the customer's willingness to buy. Whether or not a feature actually is used was out of consideration. | User research | User behavioral data | 10.1109/CLOUD.2013.33 | http://han.bg.pg.edu.pl/han/web-of-science/apps.webofknowledge.com/full_record.do?product=WOS&search_mode=GeneralSearch&qid=2&SID=E2GDNEgElWSeeR852w7&page=9&doc=84&cacheurlFromRightClick=no | Analytics for Product Planning: In-depth Interview Study with SaaS Product Managers
Backward Snowballing | 36 | TRUE | In other words, the alignment of product, project and business decisions is a major problem in the software industry. | Product knowledge management | sharing knowledge | https://doi.org/10.1016/j.sysarc.2007.12.004 | https://www-1sciencedirect-1com-1000060ww1641.han.bg.pg.edu.pl/science/article/pii/S1383762107001348 | A product management challenge: Creating software product value through requirements selection
Backward Snowballing | 36 | TRUE | VBRE is a very young area of academic study, however, the problem of creating product value through requirements selection and prioritization is real to the development of software products in today’s competitive environment. | Requirements engineering | prioritisation, requirements management | https://doi.org/10.1016/j.sysarc.2007.12.004 | https://www-1sciencedirect-1com-1000060ww1641.han.bg.pg.edu.pl/science/article/pii/S1383762107001348 | A product management challenge: Creating software product value through requirements selection
Backward Snowballing | 36 | TRUE | In summary, while product managers are focussing on business perspective and developers are focussing on product perspectives, sales/project managers will be more concerned with project perspective. Interestingly stakeholders are not always aware of their own value propositions, which can often only be elicited through experience in the problem domain [2]. Additionally only a limited number of companies in the software business are able to define or measure value from their customers’ perspectives despite many describing the achievement of this as having “never been more important” | Requirements engineering | stakeholders management | https://doi.org/10.1016/j.sysarc.2007.12.004 | https://www-1sciencedirect-1com-1000060ww1641.han.bg.pg.edu.pl/science/article/pii/S1383762107001348 | A product management challenge: Creating software product value through requirements selection
Backward Snowballing | 37 | TRUE | The challenge in many IT and software companies lies in between sales/marketing, strategy/product management and technical/R&D management. Not that the people donot talk to each other, but nobody has the formal lead to drive successful product execution. | Product knowledge management, Requirements engineering | sharing knowledge, stakeholders management | https://doi.org/10.1016/j.jss.2006.09.017 | https://www-1sciencedirect-1com-1000060ww1641.han.bg.pg.edu.pl/science/article/pii/S0164121206002615 | C. Ebert, “The Impacts of Software Product Management,” Journal of Systems & Software, vol. 80, no. 6, pp. 850–861, 2007.
Backward Snowballing | 38 | TRUE | Many companies mistakenly accept a definition that presumes product management is a collective term used to describe the broad sum of diverse activities performed in the interest of delivering a particular product to market. Such a broad definition, used by many companies today, is the root cause of much grief and problems because it lacks the professional focus needed to be successful, and allows virtually any product-related task to be assigned to the product manager. | Organisational - operational | responsibilities | 10.1007/978-3-319-49998-7 | https://link-1springer-1com-100005due004d.han.bg.pg.edu.pl/book/10.1007/978-3-319-49998-7 | G. Steinhardt, The Product Manager’s Toolkit: Methodologies, Processes and Tasks in High-Tech Product Management. Springer, 2017.
Backward Snowballing | 38 | TRUE | In some companies, the Product Marketing Manager and Product Manager are interchangeable titles as they both relate to the same function and individual. This inconsistency further causes functional problems within companies and across industries. | Organisational - operational | responsibilities | 10.1007/978-3-319-49998-7 | https://link-1springer-1com-100005due004d.han.bg.pg.edu.pl/book/10.1007/978-3-319-49998-7 | G. Steinhardt, The Product Manager’s Toolkit: Methodologies, Processes and Tasks in High-Tech Product Management. Springer, 2017.
Backward Snowballing | 38 | TRUE | It is utterly problematic to have different types and levels of information mixed and stored in one place. By aggregating all diverse product and project information in one centralized container it is very easy and quick to lose focus and context of the information. It becomes increasingly difficult and challenging—as the product grows—to realize the market problem or the scope and architecture of the solution that is being developed. | Product knowledge management | sharing knowledge, documentation | 10.1007/978-3-319-49998-7 | https://link-1springer-1com-100005due004d.han.bg.pg.edu.pl/book/10.1007/978-3-319-49998-7 | G. Steinhardt, The Product Manager’s Toolkit: Methodologies, Processes and Tasks in High-Tech Product Management. Springer, 2017.
Backward Snowballing | 38 | TRUE | The converted product manager now found himself constantly serving the development team and acting as a Scrum product owner, a managerial role that according to scrum is responsible for defining, prioritizing, and maintaining Product Backlog Items (PBI) which are contained in the product backlog. The problem is that by Scrum’s own definition the Scrum product backlog contains everything related to the product, and therefore by inference the Scrum product owner becomes responsible for everything related to the product. This is a formula for an unavoidable failure because the product owner role cannot intrinsically scale to accommodate complex or large software development projects | Organisational - operational | responsibilities | 10.1007/978-3-319-49998-7 | https://link-1springer-1com-100005due004d.han.bg.pg.edu.pl/book/10.1007/978-3-319-49998-7 | G. Steinhardt, The Product Manager’s Toolkit: Methodologies, Processes and Tasks in High-Tech Product Management. Springer, 2017.
Backward Snowballing | 38 | TRUE | These free interpretations invariably led to the ever-familiar challenges that the majority of product managers encounter daily. These challenges can be caused by a combination of the following: ambiguous role definition, imbalanced relationships with other departments, overlapping responsibilities, an overwhelming volume of activities, a lack of processes, poorly defined processes, no definitive methodology, and a shortage of uniform work tools in the profession | Organisational - operational, Requirement Engineering | responsibilities, stakeholders management, tools | 10.1007/978-3-319-49998-7 | https://link-1springer-1com-100005due004d.han.bg.pg.edu.pl/book/10.1007/978-3-319-49998-7 | G. Steinhardt, The Product Manager’s Toolkit: Methodologies, Processes and Tasks in High-Tech Product Management. Springer, 2017.
Backward Snowballing | 39 | TRUE | We often focus too much on technology and not enough on value. Features are lined up like a laundry list, yet only half of the originally allocated requirements appear in the final product release | Requirements engineering | requirements management, priroritization | 10.1109/MS.2014.72 | https://ieeexplore-1ieee-1org-1000007ww164b.han.bg.pg.edu.pl/document/6802984 | C. Ebert, “Software Product Management,” Crosstalk, vol. 22, no. 1, pp. 15–19, 2009.
Backward Snowballing | 39 | TRUE | We often find that product management is more of a role label than an effective function that leads the product. As a senior manager with whom we worked pointed out, “We had many so-called product managers who were just promoted from a technical role without a clue on the business needs and skills they should have.” Consequently, many product managers aren't content with their role and often blame “politics” for not achieving their missions. Needless to say, these product managers neither lead their product nor master their role. | Team | unqualified people | 10.1109/MS.2014.72 | https://ieeexplore-1ieee-1org-1000007ww164b.han.bg.pg.edu.pl/document/6802984 | C. Ebert, “Software Product Management,” Crosstalk, vol. 22, no. 1, pp. 15–19, 2009.
Backward Snowballing | 39 | TRUE | These root causes included business cases that were never reevaluated, unbalanced portfolios that strangle new products, insufficient management of new releases and service efforts, and lack of vision, which caused requirements to continuously change. | Requirements managemenet | requirements management, priroritization | 10.1109/MS.2014.72 | https://ieeexplore-1ieee-1org-1000007ww164b.han.bg.pg.edu.pl/document/6802984 | C. Ebert, “Software Product Management,” Crosstalk, vol. 22, no. 1, pp. 15–19, 2009.
Backward Snowballing | 40 | TRUE | This randomness of decision-making was typically accompanied by severe communication problems between IT and the business units. | Organisational - operational, Team | decision making process, communication |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Some issues and problems will always be neglected because no one feels responsible. Product management is therefore often misunderstood as being a universal caretaker responsible for all such issues and problems. Corporate management must deal with this problem by defining and delimiting the scope of all relevant tasks. | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | We have experienced many unproductive projects and highly productive employees who perform ongoing jobs. Furthermore, ignorance of ongoing critical tasks, such as market analysis or personnel development, tends to create enormous problems in the medium term for the company as a whole. Our observations show that good corporate management and a good working atmosphere help significantly to influence productivity. | Organisational - strategy, Team | market research, motivation |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Since the mid-1990’s, a lot of companies have worked with external people in locations with a considerably lower cost level. This is known as near-shore or off-shore outsourcing. In the software area, some companies have managed to make this work and save money, but in a lot of cases the hidden cost generated by communication overhead and lost time due to communication problems turned out to eat up the calculated savings. | Organisational - operational, team | partnership management, communication |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Like all business processes that are cross-organizational and require the cooperation of different organizational units, the requirements management process is a big problem in a lot of companies. | Requirements engineering | requirements management |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Release planning becomes a complex multi-dimensional problem when product families, lines, or platforms are involved. | Software product line / Software development process | release cycle speed |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | At least the use of development tools ensured that there were no data synchronization problems between Product Management and Development. Conversely, the choice of an inappropriate tool can have devastating effects on an organization | Organisational - operational | tools |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Software is malleable, so even existing products can evolve in many different directions—which can easily lead to uncontrolled growth and lack of alignment between portfolio products, which may create portfolio gaps or unintended overlaps between products that result in positioning and sales problems within the portfolio. | Organisational - operational | strategy |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | In those companies, executive management, as well as the managers of the other organizational units, tend to misuse the product manager as caretaker for any problem that | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Lack of education and standardization in SPM are not the only challenges today. | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Although the respondents reported unclear definition of the role as one of the main challenges, we tend to consider this lack of clarity as a result of other challenges like too many responsibilities and little authority. | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | Another risk of being a “multipurpose person” is receiving more and more requests to fill many tasks ranging from development to user experience design to marketing, sales and support. However, while being in charge of many activities critical to the product success, product managers rarely have authority in practice | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | The other reported challenges were related to general challenges of development and management of software products: customer understanding, rapidly changing environment, prioritization, coordination, and resource management. | Organisational - operational, Requirement Engineering | prioritization, user centered design |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | On the value side the challenge is threefold: often benefits and value are of a qualitative nature that is difficult to convert into actual earnings or savings; the monetary benefits may (and usually do) vary from customer to customer; and the benefits/value may be realized over an extended time period after the release is made available. | Organisational - strategy | Strategy, Business model, |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | The biggest challenges are the resolution of conflicts among stakeholders, a software architecture and runtime environment that allow micro-changes during runtime, integration with slower processes of the organization, and the setup of a tool suite that enables continuous delivery. Orchestration challenges typically exist: • Between product managers for different products in the organization’s portfolio due to resource allocation, budget allocation, positioning of products against each other within the portfolio, functional scope, interfaces, release dates, and bigger requirements that require parts of the implementation in different products with resulting dependencies, • Between sales and development unit due to short-term goals and individual customers versus long-term abstract perspectives, • Between product manager and development unit due to release scope and dates, resource allocation, and project planning (overall project portfolio, not details in each project), • Between product manager and marketing unit due to brand marketing versus product marketing, and • Between product manager and sales and distribution unit due to discounting, the reliability of commitments regarding the sales volume of the product, reporting granularity, customer commitments and what can be delivered realistically versus everything that customers want. | Requirements engineering, Organisational - operational | stakeholders management, system architecture, tools, continuous integration, requirements management, |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 40 | TRUE | The SPM challenge is to focus on the strategic and important items in such a high-pace environment. | Organisational - strategy | strategy |  | https://link.springer.com/book/10.1007/978-3-642-55140-6 | S. A. Fricker, “Software Product Management,” in Software for People, A. Maedche, A. Botzenhardt, and L. Neer, Eds. Springer Berlin Heidelberg, 2012, pp. 53–81.
Backward Snowballing | 41 | TRUE | Problem 1 Long Release Cycle The main source of waste here is the sequential nature of work in units, which leads to constant switching between activi-ties for each department. In the described situation, every department was an isolated unit acting independently and focusing on its own work instead of thinking about the whole product. The most common bottleneck was development. For people outside the development department, it looked like a black box with a feature list as an input and the product with partially implemented features as an output. | Organisational - operational | responsibitlies, distributed teams |  | https://www.researchgate.net/publication/260649306_Lean_Solutions_to_Software_Product_Management_Problems | A. Maglyas, U. Nikula, and K. Smolander, “Lean Solutions to Software Product Management" Problems,” IEEE Software, vol. 29, no. 5, pp. 40–46, 2012.
Backward Snowballing | 41 | TRUE | Problem 2: No Metrics for Evaluating Work In all the organizations, the product managers responsible for the whole product had no key performance indicators (KPIs). | User research, Organisational - operational | business intelligence, responsibilities |  | https://www.researchgate.net/publication/260649306_Lean_Solutions_to_Software_Product_Management_Problems | A. Maglyas, U. Nikula, and K. Smolander, “Lean Solutions to Software Product Management" Problems,” IEEE Software, vol. 29, no. 5, pp. 40–46, 2012.
Backward Snowballing | 41 | TRUE | Problem 3: Collaboration between Organizations and Customers Some of the organizations were very customer oriented, but not all of them. In an extreme case, we observed speculations about customers’ needs and wishes when there was no collaboration with the customers at all: Consequently, fitting customer needs takes a lot of time. The product release will possibly be delayed, and the organization might lose the opportunity to hit the market earlier than its competitors. | User research, Requirement engineering | user centeted design, user involvement |  | https://www.researchgate.net/publication/260649306_Lean_Solutions_to_Software_Product_Management_Problems | A. Maglyas, U. Nikula, and K. Smolander, “Lean Solutions to Software Product Management" Problems,” IEEE Software, vol. 29, no. 5, pp. 40–46, 2012.
Backward Snowballing | 41 | TRUE | Problem 4: Short-Term Thinking Almost all the studied organizations concentrated on short-term actions, such as implementing trendy, new, and modern development processes without a deep analysis of their outcomes, or developing many products in parallel without understanding the company’s core business. Even the top managers weren’t ready to discuss their plans on the one-year horizon. All but one of the studied organizations (F) developed strategies for one year only. Consequently, the organizations frequently change their vision and strategy, trying to match it with external conditions. | Organisational - strategic | Strategy |  | https://www.researchgate.net/publication/260649306_Lean_Solutions_to_Software_Product_Management_Problems | A. Maglyas, U. Nikula, and K. Smolander, “Lean Solutions to Software Product Management" Problems,” IEEE Software, vol. 29, no. 5, pp. 40–46, 2012.
Backward Snowballing | 41 | TRUE | Problem 5: Trying to Change Instantly The problem of radical changes didn’t come up in extra-large and large organizations (A–D). It seemed that they know from previous experiences that radical changes are risky.11,14 Therefore, they’re more comfortable with carefully planning and preparing for each initiative for a change, and even learning to manage the increasing complexity of SPM within their large organizations. | Organisational - operational | responsibilities |  | https://www.researchgate.net/publication/260649306_Lean_Solutions_to_Software_Product_Management_Problems | A. Maglyas, U. Nikula, and K. Smolander, “Lean Solutions to Software Product Management" Problems,” IEEE Software, vol. 29, no. 5, pp. 40–46, 2012.
Backward Snowballing | 42 | TRUE | The strategic and tactical planning are tightly coupled together, but the main problem is the balance between them | Organisational - strategic, Organisational - operational | strategy, responsibilities |  | https://www.researchgate.net/publication/288117874_Comparison_of_Software_Product_Management_Practices_in_SMEs_and_Large_Enterprises | A. Maglyas, U. Nikula, and K. Smolander, “Comparison of Software Product Management Practices in SMEs and Large Enterprises
Backward Snowballing | 42 | TRUE | In comparison, their colleagues from SMEs did not have authority to make decisions. In SMEs most decisions were made by top management and product managers acted as advisors and facilitators in solving problems arising between departments. | Organisational - operational | decision making process, responsibilities |  | https://www.researchgate.net/publication/288117874_Comparison_of_Software_Product_Management_Practices_in_SMEs_and_Large_Enterprises | A. Maglyas, U. Nikula, and K. Smolander, “Comparison of Software Product Management Practices in SMEs and Large Enterprises
Backward Snowballing | 43 | TRUE | The participants also discussed actively issues related to roadmapping, and especially to aligning problems with business goals. | Requirements engineering, Organisational - strategic | product roadmap, strategy |  | https://ieeexplore.ieee.org/document/6345812 | A. Maglyas, U. Nikula, and K. Smolander, “What do practitioners mean when they talk about product management?,” presented at the 20th IEEE International Requirements Engineering Conference (RE), 2012, pp. 261 –266.
Backward Snowballing | 43 | TRUE | There were also attempts to explain the meaning of product management by using the product manager's role. The absolutely dominating viewpoint was that the product manager is the product mini-CEO (the category was identified 24 times), also referred to as the product champion. The main problem with these responses was that after attaching the label mini-CEO to the product manager, there were no explanations to what the mini-CEO should do. | Organisational - operational | responsibilities |  | https://ieeexplore.ieee.org/document/6345812 | A. Maglyas, U. Nikula, and K. Smolander, “What do practitioners mean when they talk about product management?,” presented at the 20th IEEE International Requirements Engineering Conference (RE), 2012, pp. 261 –266.
Backward Snowballing | 44 | TRUE | none |  |  |  | https://www.researchgate.net/publication/267271367_The_Preliminary_Results_from_the_Software_Product_Management_State-of-Practice_Survey | A. Maglyas and S. Fricker, “The Preliminary Results from the Software Product Management State- of-Practice Survey,” in Software Business. Towards Continuous Value Delivery, Springer International Publishing, 2014, pp. 295–300.
Backward Snowballing | 45 | TRUE | Another problem is the integration of a software product with other systems. Customers cannot expect that all their requirements are met, which may lead to a software product that does not integrate with their existing systems. | Requirements engineering | requirements management |  | https://dspace.library.uu.nl/handle/1874/19439 | Weerd, I. van de; Brinkkemper, S.; Nieuwenhuis, R.; Versendaal, J.M.; Bijlsma, A. (2006) A reference framework for software product management
Backward Snowballing | 45 | TRUE | The organization of requirements and the tracking of changes in the design are very complex. Also, due to the ease of making changes, the release frequency is relatively high in comparison with non-software products. Finally, the product manager has a lot of responsibilities regarding the product functionality, but has not the management authority over the development team, so decision making requires consent of many players. | Requirements engineering, user research | product design, requirements management |  | https://dspace.library.uu.nl/handle/1874/19439 | Weerd, I. van de; Brinkkemper, S.; Nieuwenhuis, R.; Versendaal, J.M.; Bijlsma, A. (2006) A reference framework for software product management
Forward Snowballing | 46 |  | Long-term user needs driven research helps firms to plan short- and long-term product development and allow design managers to prioritize problems they should solve first along a timeline. | Requirements engineering | prioritisation, product design |  | https://ieeexplore.ieee.org/abstract/document/9250585 | User-Centered Design Roadmapping: Anchoring Roadmapping in Customer Value Before Technology Selection
Forward Snowballing | 47 | TRUE | Frequently, these business requirements or business deliverables include a detailed description of the solution “the business” would like “IT to implement.” Unfortunately, these requirements are not originated by the users, but rather by the business management, COOs, process offices or other layers between the end user and the delivery/development team. Generally, this is where the problems usually start as many of these requests create only limited value, and together they do not form a coherent product. | User research | stakeholders management, prioritisation |  | https://link.springer.com/book/10.1007%2F978-3-030-19871-8 | Software Product Management. Finding the Right Balance for YourProduct Inc.
Forward Snowballing | 47 | TRUE | Fig. 1.18 shows that only for less than 22% surveyed the role of product managers is clearly defined. As we will see later, that is a set-up for failure or at least poses severe problems for product managers. No wonder that lack of role clarity made it to the top three product management challenges. The role of executives is significant in this matter. In organi | Organisational - operational | responsibilities |  | https://link.springer.com/book/10.1007%2F978-3-030-19871-8 | Software Product Management. Finding the Right Balance for YourProduct Inc.
Forward Snowballing | 47 | TRUE | I have worked with many product teams that had skilled individuals, motivated and ready to rock, to solve a real problem. But they could not get a great product out or keep a brilliant product in the market because they were missing focus and alignment. The risk increases with the size of the organizations. This lack of focus and alignment frequently leads to declining engagement amongst the product team members | Organisational - strategic, Requirements engineering | strategy, prioritisation |  | https://link.springer.com/book/10.1007%2F978-3-030-19871-8 | Software Product Management. Finding the Right Balance for YourProduct Inc.
Forward Snowballing | 47 | TRUE | In my experience, the part of requirements gathering and capturing domain knowledge is good organization and structure.. Otherwise the team might not see the wood for the trees anymore, drown in tons of ideas, information snippets, solution approaches, and a variety of document formats, and that’s not including all the information available to build an outstanding product. | Requirements engineering, Product knowledge management | documentation, requirements management |  | https://link.springer.com/book/10.1007%2F978-3-030-19871-8 | Software Product Management. Finding the Right Balance for YourProduct Inc.
Forward Snowballing | 47 | TRUE | Summarize why prioritization is hard: Product Development and Product Development Planning is a complex problem due to many directions, stakeholders, contradicting objectives, constraints and boundaries—all at the same time | Requirements engineering, Organisational - strategic | prioritisation, stakeholder management, strategy |  | https://link.springer.com/book/10.1007%2F978-3-030-19871-8 | Software Product Management. Finding the Right Balance for YourProduct Inc.
Forward Snowballing | 48 | TRUE | Overwhelming processes, unclear responsibilities of software product managers along with premature decision-making practices and moving targets are often named as prime challenges. | Organisational - operational | responsibilities, decisin making process |  | http://ceur-ws.org/Vol-2305/paper13.pdf | Decision-making in Software Product Management: Identifying Research Directions from Practice
Forward Snowballing | 48 | TRUE | The key challenges in the early days of evidence-based management were lack of data that could be turned into pieces of evidence and tweaking the techniques that could help to get at least some proxy data. | Software product Line/Software development process, User research | user bahavioral data, data collection |  | http://ceur-ws.org/Vol-2305/paper13.pdf | Decision-making in Software Product Management: Identifying Research Directions from Practice
Forward Snowballing | 48 | TRUE | There is a pervasive need for easy-to-use approaches and frameworks to support evidence-based SPM migration. Lack of clear vision regarding typology of evidences that could be served for informed decision-making could be names as prime obstacles towards broader implementation of evidence-based software product management. These issues are supplemented by immature communication and knowledge sharing practices, poor integration between various SPM tools and systems used and scarcity of competency in data analytics, simulation modeling, and knowledge management. | Team, Organisational - operational, Software product Line/Software development process | communication, tools, data collection |  | http://ceur-ws.org/Vol-2305/paper13.pdf | Decision-making in Software Product Management: Identifying Research Directions from Practice