| ERIC strategy | implementation activities | Format | Participants | Content | Date |
| --- | --- | --- | --- | --- | --- |
| Conduct educational Meetings | Trainer training | In person | Trainers Clinical study coordination | Procedure of the study Implementation of the training Trainer tasks | September 2022 |
| Conduct educational meetings | Social service training | In person | Clinic social service Insurance social service Clinical study coordination project evaluation | Coordination of the interface between clinic and insurance social service | September 2022 |
| conduct educational meetings | Clinician training | Online | Clinicians | Procedure of the study Clinician tasks | September 2022 |
| conduct educational meetings | Software training | Online | Trainers Clinical study coordination Clinical study monitoring Project evaluation Clinical study doctors Clinic social service Insurance social service University Ulm | Handling of the software | Part 1: August 2022 Part 2: October 2022 |
| conduct educational meetings | Tablet training | In person | Trainers Clinical study coordination Clinic social service Insurance social service | Handling of the tablets | September 2022 |
| involve patients/consumers and family members | Patient advisory board | In person | Representatives of patients Researchers (clinical study coordination; clinical study doctors; project evaluation) | Part 1: Presentation of the project; Discussion of study material Part 2: Presentation of results of the first meeting; Testing of the training app and tablets Part 3: Optimization of Recruitment; Acceptance of tablets Part 4: to be determined | Part 1: April 2022 Part 2: July 2022 Part 3: May 2023 Part 4: 3. Quarter 2024 |
| organize clinician implementation team meetings | Trainer workshop | Online | Trainers Clinical study coordination | Discussion of current changes and/ or problems; collegial exchange; ascertain standard procedure | 1 meeting per quarter (continuously) |