Table I: Causes of Design Changes in Construction Projects

| Category | Cause of Design Change | Studies |
| --- | --- | --- |
| Client | Requirement and Specification changes | Do et al. (2023); Selcuk et al. (2022); Elhusseiny et al. (2021); Aladağ and Işık (2019) |
|  | Value Engineering (e.g., cost savings) | Gashaw and Jilcha (2023); Selcuk et al. (2022); Shen and Ying (2022); Soman et al. (2020) |
|  | Vagueness of the client brief | Do et al. (2023); Sanni-Anibire et al. (2020); Chen et al. (2020); |
|  | Scope adjustment, addition, or omission | Tariq and Gardezi (2022); Elhusseiny et al. (2021); Chen et al. (2020); |
|  | Extra requirements | Padala and Maheswari (2023); Sanni-Anibire et al. (2020); Aladağ and Işık (2019) |
|  | Change of project financing | Gashaw and Jilcha (2023); Egwin et al. (2021); Soman et al. (2020) |
|  | Ineffective decision-making | Barqawi et al. (2022); Elhusseiny et al. (2021); Soman et al. (2020); Aladağ and Işık (2019) |
|  | Change the usage of the project | Do et al. (2023); Barqawi et al. (2022); Sanni-Anibire et al. (2020); Chen et al. (2020) |
| Consultant | Lack of coordination between different disciplines | Gurgun et al. (2022); Selcuk et al. (2022); Gunduz and Al-Naimi (2021); Soman et al. (2020). |
|  | Lack of understanding of the owner’s requirements | Padala and Maheswari (2023); Selcuk et al. (2022); Soman et al. (2020); Aladağ and Işık (2019) |
|  | Design documents errors or inconsistencies | Selcuk et al. (2022); Gharaibeh et al. (2020); Chen et al. (2020); Viles et al. (2020) |
|  | Constructability issues | Shen and Ying (2022); Tariq and Gardezi (2022); Aladağ and Işık (2019) |
|  | Quality specifications compliance | Stewart and Shirvan (2023); Chen et al. (2020); Bortolini et al. (2019) |
| Contractor | Change of methods of construction | Egwin et al. (2021); Gharaibeh et al. (2020); Alsuliman (2019) |
|  | Enhancing buildability | Zeng et al. (2022); Barqawi et al. (2022); Chen et al. (2020); Bortolini et al. (2019) |
|  | Material shortage | Gunduz and Al-Naimi (2021); Gharaibeh et al. (2020); Alsuliman (2019) |
|  | Fixing construction errors | Do et al. (2023); Barqawi et al. (2022); Soman et al. (2020); Aladağ and Işık (2019) |
|  | Improvement of work quality | Shen and Ying (2022); Barqawi et al. (2022); Viles et al. (2020); Aladağ and Işık (2019) |
|  | Improving health and safety aspects | Stewart and Shirvan (2023); Aladağ and Işık (2019); Bortolini et al. (2019) |
|  | Coordination of drawings and design due to discrepancies | Padala and Maheswari (2023); Do et al. (2023); Gunduz and Al-Naimi (2021) |
|  | Technical issues from suppliers | Do et al. (2023); Barqawi et al. (2022); Chen et al. (2020); Viles et al. (2020) |
|  | Lack of workers’ skills | Gurgun et al. (2022); Aladağ and Işık (2019); Soman et al. (2020) |
| Site related (contextual factor) | Geotechnical Problems | Stewart and Shirvan (2023); Tariq and Gardezi (2022); |
|  | Clash with neighboring structures / buildings | Gurgun et al. (2022); Elhusseiny et al. (2021); Chen et al. (2020) |
|  | Undiscovered utilities or services on site | Egwin et al. (2021); Chen et al. (2020); Alsuliman (2019) |

Table II: Effects of Design Changes in Construction Projects

| Impact of design changes | Studies |
| --- | --- |
| Rework or revision of work | Zeng et al. (2022); Barqawi et al., (2022); Chen et al. (2020); Bortolini et al. (2019) |
| Schedule Delay | Barqawi et al., (2022); Chen et al. (2020); Soman et al. (2020); Aladağ and Işık (2019) |
| Cost overruns | Do et al. (2023); Barqawi et al. (2022); Gharaibeh et al. (2020). |
| Excessive claims/disputes | Chen et al. (2020); Bortolini et al. (2019); Gurgun et al. (2022) |
| Loss of productivity / work rhythm | Egwin et al. (2021); Gharaibeh et al. (2020); Alsuliman (2019) |
| Coordination issues and errors | Stewart and Shirvan (2023); Aladağ and Işık (2019); Bortolini et al. (2019) |
| Lower moral of work force | Gurgun et al. (2022); Soman et al. (2020); Aladağ and Işık (2019) |
| Poor construction quality | Shen and Ying (2022); Tariq and Gardezi (2022); Aladağ and Işık (2019) |

Table III: List of Participants in the study

| Interviewee | Stakeholder | Designation |
| --- | --- | --- |
| #1 | Contractor | Construction Manager |
| #2 | Contractor | Senior Architectural Engineer |
| #3 | Sub-contractor | Senior Project Manager |
| #4 | Consultant | Senior Project Manager |
| #5 | Consultant | Project Engineer |
| #6 | Sub-contractor | MEP Coordinator |

Table IV: Responses from the validation session conducted with the three construction firms in the U.A.E

| Thematic Area | Validation Focus | Summary of Responses |
| --- | --- | --- |
| Construct Coverage | Captures key triggers of design changes and stakeholder roles | Participants consistently agreed that the model accounted for the main drivers of design changes in UAE projects, such as client-initiated variations, regulatory and authority approvals, incomplete or late design information, and design coordination clashes. All six project managers confirmed that the major stakeholders were well represented (client, consultants, contractors, subcontractors, and authorities). One participant noted that the model could more explicitly acknowledge the role of project management consultants (PMCs), who often mediate design changes on large projects. Overall, no critical omissions were identified, and the breadth of coverage was regarded as comprehensive. |
| Accuray of capturing issues | Accuracy of relationships, feedback loops, and escalation paths | The feedback loops linking design changes, rework, and downstream scheduling delays were described as “realistic” and “directly reflective of on-site experience.” Several participants highlighted the usefulness of representing escalation pathways, such as how unresolved design clashes can trigger ripple effects across multiple disciplines. One participant from Firm B suggested greater emphasis on supply chain constraints as amplifiers of design change delays, particularly for imported materials. Others recommended clarifying the strength of influence between regulatory approvals and subsequent redesign cycles, as this was seen as a particularly strong cause of delay in the UAE context. |
| Operational Feasibility | Alignment with available project records and data sources | All participants confirmed that the constructs mapped well onto existing project documentation, such as RFI logs, change orders, shop drawing submissions, and authority approval records. This was viewed as a strength because it means the model can be operationalised using data that project teams already collect. However, two managers raised concerns about the variability in the quality of subcontractor documentation, which can limit data accuracy. Another participant noted that while the model was data-friendly, smaller firms may face challenges in systematically capturing the required information without digital tools. |
| Applicability | Transferability across project types and procurement contexts | The model was generally regarded as applicable to both building and infrastructure projects under common UAE procurement arrangements. Project managers noted that the logic of design change impacts holds across a variety of project sizes, from mid-rise commercial developments to large-scale infrastructure. Nonetheless, one participant cautioned that projects with highly specialised technical requirements, such as oil and gas facilities, may require additional constructs (e.g., interface with international safety standards). Another suggested that adaptation may also be needed for design-and-build contracts, where contractor-led design introduces different dynamics of change. |
| Predictive and Solution-Oriented Value | Ability to anticipate CoD-related delays and support proactive decisions | Participants unanimously highlighted the potential of the model as a forward-looking tool. They reported that it could help anticipate design-related risks by making causal pathways more transparent. Several noted that the model could support practical mitigation measures such as establishing clear design freeze points, resequencing activities to absorb late design inputs, or strengthening change management protocols. One project manager commented that the model “would help to avoid a major dispute on a previous project” by clarifying the chain of causation for a design-related delay claim. This reinforced the view that the model has tangible value in both risk management and dispute avoidance. |

Table V: Examples on how to use the model developed to manage CoD Events

| CoD event | Stakeholders Impacted | Implications on Project Phases | Project factors |
| --- | --- | --- | --- |
| Change of Curtain Wall System specification | Design Team: - Design Adjustment - Structural calculations Contractor Team: - Procurement Client: - Budget Implications | Design: - Miscoordination between project team members Construction: - Procurement and scheduling Post-construction: - Maintenance Management | Site Conditions: - Site machinery requirements - Logistics Waste |