Supplementary tables

Table 9 Respondents Questionnaire Response Rate

| Respondents Category | Number of questioners Distributed | Number of questioners Returned | Percentage of response rate (%) |
| --- | --- | --- | --- |
| Contractor | 30 | 26 | 86.7 |
| Consultant | 17 | 15 | 88.2 |
| client | 3 | 3 | 100.0 |
| Total | 50 | 44 | 88.0 |

Table 10 Experience in Job

| Type of organization | Frequency and percentage | Job Experience in years |  |  |  |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | <=5 years | 6-10 | 11 -15 | >=16 |  |  |
| Contractor | frequency | 2 | 15 | 8 | 1 | 26 |  |
|  | Percentage | 7.7% | 57.7% | 30.8% | 3.8% | 100% |  |
| Consultant | frequency | 2 | 10 | 3 |  | 15 |  |
|  | Percentage | 13.3% | 66.7% | 20.0% |  | 100% |  |
| Client | frequency | 1 | 2 |  |  | 3 |  |
|  | Percentage | 33.3% | 66.7% |  |  | 100% |  |
| Total | frequency | 5 | 27 | 11 | 1 | 44 |  |
|  | Percentage | 11.4% | 61.4% | 25.0% | 2.3% | 100% |  |

Table 11 Respondents Positions

|  | contract administration | project supervisor | project manager | Site Engineer |
| --- | --- | --- | --- | --- |
| Contractor | 9 | 6 | 3 | 8 |
| Consultant | 2 | 0 | 3 | 10 |
| Client | 0 | 0 | 0 | 3 |

Table 12 Level of implementation of EVMS from consultant view

| No | EVMS technical implementation | Degree of Implementation | Frequency Consult. | % |
| --- | --- | --- | --- | --- |
| 1 | A work breakdown structure to a manageable level | Highly | 9 | 60.0% |
|  |  | Moderately | 6 | 40.0% |
| 2 | Assign unambiguous management responsibility | Moderately | 7 | 46.7% |
|  |  | Least | 8 | 53.3% |
| 3 | Objectively measure the progress of physical work | Highly | 5 | 33.3% |
|  |  | Moderately | 10 | 66.7% |
| 4 | Develop a time-phased budget for each work task | Moderately | 11 | 73.3% |
|  |  | Least | 4 | 26.7% |
| 5 | Record usage of resource expenditures during project execution | Moderately | 11 | 73.3% |
|  |  | Least | 4 | 26.7% |
| 6 | Maintain the integrity of PMB throughout the project | Moderately | 12 | 80.0% |
|  |  | Least | 3 | 20.0% |
| 7 | Identify variances in the detail needed by program management. | Least | 15 | 100.0% |
| 8 | Implement managerial actions taken as the result of EV | Least | 15 | 100.0% |
| 9 | Analyses and forecast cost/schedule performance | Moderately | 15 | 100.0% |
| 10 | Report performance Problems and or take actions | Moderately | 9 | 60.0% |
|  |  | Least | 6 | 40.0% |
| 11 | Document changes to the performance measurement baseline. | Moderately | 11 | 73.3% |
|  |  | Least | 4 | 26.7% |

Table 13 Level of implementation of EVMS from contractor view

| No | EVMS technical implementation | Degree of Implementation | Frequency | % |
| --- | --- | --- | --- | --- |
| 1 | A work breakdown structure to a manageable level | Highly | 10 | 38.5% |
|  |  | Moderately | 16 | 61.5% |
| 2 | Assign unambiguous management responsibility | Moderately | 9 | 34.6% |
|  |  | Least | 17 | 65.4% |
| 3 | Objectively measure the progress of physical work | Highly | 10 | 38.5% |
|  |  | Moderately | 16 | 61.5% |
| 4 | Develop a time-phased budget for each work task | Moderately | 20 | 76.9% |
|  |  | Least | 6 | 23.1% |
| 5 | Record usage of resource expenditures during project execution | Moderately | 19 | 73.1% |
|  |  | Least | 7 | 26.9% |
| 6 | Maintain the integrity of PMB throughout the project | Moderately | 15 | 57.7% |
|  |  | Least | 11 | 42.3% |
| 7 | Identify variances in the detail needed by program management. | Least | 26 | 100.0% |
| 8 | Implement managerial actions taken as the result of earned value | Least | 26 | 100.0% |
| 9 | Analyses and forecast cost/schedule performance | Moderately | 26 | 100.0% |
| 10 | Project performance problems and/or take actions | Moderately | 15 | 57.7% |
|  |  | Least | 11 | 42.3% |
| 11 | Document changes to the performance measurement baseline. | Moderately | 16 | 61.5% |
|  |  | Least | 10 | 38.5% |

Table 14 Level of implementation of EVMS from the client view

| No | EVMS technical implementation | Degree of Implementation | Frequency client | % client |
| --- | --- | --- | --- | --- |
| 1 | A work breakdown structure to a manageable level | Highly |  | 0 |
|  |  | Moderately | 3 | 100.0% |
| 2 | Assign unambiguous management responsibility | Moderately | 1 | 33.3% |
|  |  | Least | 2 | 66.7% |
| 3 | Objectively measure the progress of physical work | Highly |  | 0.0% |
|  |  | Moderately | 3 | 100.0% |
| 4 | Develop a time-phased budget for each work task | Moderately | 3 | 100.0% |
|  |  | Least |  | 0.0% |
| 5 | Record usage of resource expenditures during project execution | Moderately | 3 | 100.0% |
|  |  | Least |  | 0.0% |
| 6 | Maintain the integrity of PMB throughout the project | Moderately | 2 | 66.7% |
|  |  | Least | 1 | 33.3% |
| 7 | Identify variances in the detail needed by program management. | Least | 3 | 100.0% |
| 8 | Implement managerial actions taken as the result of earned value | Least | 3 | 100.0% |
| 9 | Analyses and forecast cost/schedule performance | Moderately | 3 | 100.0% |
| 10 | Report performance problems and/or take actions | Moderately | 2 | 66.7% |
|  |  | Least | 1 | 33.3% |
| 11 | Document changes to the performance measurement baseline. | Moderately | 3 | 100.0% |
|  |  | Least |  | 0.0% |

Table 15  Level of implementation of EVMS from an Overall view

|  |  |  |  |  |  | total |  |  |  | total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Contractor | Consultant | Client |  | Contractor | Consultant | client |  |
| 1 | A work breakdown structure to a manageable level | Highly | 10 | 9 |  | 19 | 38.5% | 60.0% | 0 | 43.2% |
|  |  | Moderately | 16 | 6 | 3 | 25 | 61.5% | 40.0% | 100.0% | 56.8% |
| 2 | Assign unambiguous management responsibility | Moderately | 9 | 7 | 1 | 17 | 34.6% | 46.7% | 33.3% | 38.6% |
|  |  | Least | 17 | 8 | 2 | 27 | 65.4% | 53.3% | 66.7% | 61.4% |
| 3 | Objectively measure the progress of physical work | Highly | 10 | 5 |  | 15 | 38.5% | 33.3% | 0.0% | 34.1% |
|  |  | Moderately | 16 | 10 | 3 | 29 | 61.5% | 66.7% | 100.0% | 65.9% |
| 4 | Develop a time-phased budget for each work task | Moderately | 20 | 11 | 3 | 34 | 76.9% | 73.3% | 100.0% | 77.3% |
|  |  | Least | 6 | 4 |  | 10 | 23.1% | 26.7% | 0.0% | 22.7% |
| 5 | Record usage of resource expenditures during project execution | Moderately | 19 | 11 | 3 | 33 | 73.1% | 73.3% | 100.0% | 75.0% |
|  |  | Least | 7 | 4 |  | 11 | 26.9% | 26.7% | 0.0% | 25.0% |
| 6 | Maintain the integrity of PMB throughout the project | Moderately | 15 | 12 | 2 | 29 | 57.7% | 80.0% | 66.7% | 65.9% |
|  |  | Least | 11 | 3 | 1 | 15 | 42.3% | 20.0% | 33.3% | 34.1% |
| 7 | Identify variances in the detail needed by program management. | Least | 26 | 15 | 3 | 44 | 100.0% | 100.% | 100.0% | 100.0% |
| 8 | Implement managerial actions taken as the result of earned value | Least | 26 | 15 | 3 | 44 | 100.0% | 100.0% | 100.0% | 100.0% |
| 9 | Analyses and forecast cost/schedule performance | Least | 26 | 15 | 3 | 44 | 100.0% | 100.0% | 100.0% | 100.0% |
| 10 | Report performance problems and/or take actions | Moderately | 15 | 9 | 2 | 26 | 57.7% | 60.0% | 66.7% | 59.1% |
|  |  | Least | 11 | 6 | 1 | 18 | 42.3% | 40.0% | 33.3% | 40.9% |
| 11 | Document changes to the performance measurement baseline. | Moderately | 16 | 11 | 3 | 30 | 61.5% | 73.3% | 100.0% | 68.2% |
|  |  | Least | 10 | 4 |  | 14 | 38.5% | 26.7% | 0.0% | 31.8% |

Table 16  Schedule Analysis of Ruga Manayu water supply project

| RUGA QUARTER REPORT |  |  | Project Duration | 18.00 | Month |  |
| --- | --- | --- | --- | --- | --- | --- |
| Quarter(E.C) | Cum PV | Cum EV | SV | SPI | EAC(t) | % SV |
| Q1(2008) | 2,378,873.01 | 3,306,463.45 | 927,590.44 | 1.390 | 13 | 28% |
| Q2 (2009) | 9,528,526.58 | 3,306,463.45 | (6,222,063.13) | 0.347 | 52 | -188% |
| Q3 (2009) | 49,565,474.57 | 5,873,125.22 | (43,692,349.35) | 0.118 | 152 | -744% |
| Q4 (2009) | 69,671,178.14 | 19,621,579.70 | (50,049,598.44) | 0.282 | 64 | -255% |
| Q5 (2009) | 102,732,634.90 | 31,142,334.32 | (71,590,300.58) | 0.303 | 59 | -230% |
| Q6 (2010) | 102,732,634.90 | 33,748,458.96 | (68,984,175.94) | 0.329 | 55 | -204% |
| Q7 (2010) | 129,399,265.26 | 36,117,927.12 | (93,281,338.14) | 0.279 | 64 | -258% |
| Q8 (2010) | 143,669,790.59 | 39,624,431.29 | (104,045,359.30) | 0.276 | 65 | -263% |
| Q9 (2010) | 177,578,433.41 | 44,192,805.12 | (133,385,628.29) | 0.249 | 72 | -302% |
| Q10 (2011) | 198,466,804.02 | 44,716,992.91 | (153,749,811.11) | 0.225 | 80 | -344% |
| Q11 (2011) | 217,246,958.21 | 46,559,985.82 | (170,686,972.39) | 0.214 | 84 | -367% |
| Q12 (2011) | 228,163,196.09 | 47,529,210.35 | (180,633,985.74) | 0.208 | 86 | -380% |
| Q13 (2011) | 234,261,552.61 | 59,907,397.17 | (174,354,155.44) | 0.256 | 70 | -291% |
| Q14 (2012) | 251,572,075.43 | 60,300,041.84 | (191,272,033.59) | 0.240 | 75 | -317% |
| Q15 (2012) | 251,923,641.71 | 63,844,516.16 | (188,079,125.55) | 0.253 | 71 | -295% |
| Q16 (2012) | 263,369,591.00 | 68,477,193.11 | (194,892,397.89) | 0.260 | 69 | -285% |
| Q17 (2012) | 276,123,134.22 | 71,312,901.12 | (204,810,233.10) | 0.258 | 70 | -287% |
| Q18 (2013) | 282,091,128.66 | 71,701,491.58 | (210,389,637.08) | 0.254 | 71 | -293% |
| Q19 (2013) | 282,091,128.66 | 71,701,491.58 | (210,389,637.08) | 0.254 | 71 | -293% |
| Q20 (2013) | 285,706,311.09 | 72,152,369.48 | (213,553,941.61) | 0.253 | 71 | -296% |
| Q21 (2013) | 290,480,881.95 | 72,873,041.63 | (217,607,840.32) | 0.251 | 72 | -299% |
| Q22 (2014) | 290,480,881.95 |  |  |  |  |  |
| Q23 (2014) | 290,480,881.95 |  |  |  |  |  |

Table 17 Schedule and Cost performance Index Ruga Manayu

| Half year | SPI | CPI |
| --- | --- | --- |
| Q1(2008) | 1.390 | 1.248 |
| Q3 (2009) | 0.118 | 0.824 |
| Q5 (2009) | 0.303 | 0.927 |
| Q7 (2010) | 0.279 | 0.959 |
| Q9 (2010) | 0.249 | 0.916 |
| Q11 (2011) | 0.214 | 0.909 |
| Q13 (2011) | 0.256 | 0.918 |
| Q15 (2012) | 0.253 | 0.964 |
| Q17 (2012) | 0.258 | 0.963 |
| Q19 (2013) | 0.254 | 0.962 |
| Q21 (2013) | 0.251 | 0.955 |
| Q23 (2014) | 0.251 | 0.952 |

Table 18  Schedule analysis Kombolcha Reservoir

| Project Cost =25685194.19 ETB, Duration =15 month |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Quarterly | Cum. PV | Cum EV | SV | SPI | EAC(t) month |
| Jun-19 | 106,295.00 | 106,295.00 | 0 | 1 | 15 |
| Sep-19 | 346,128.15 | 887,839.09 | 541710.94 | 2.57 | 6 |
| Dec-19 | 14,322,694.16 | 2,242,143.99 | -12080550.17 | 0.16 | 96 |
| Mar-20 | 21,146,280.63 | 3,001,220.27 | -18145060.36 | 0.14 | 106 |
| Jun-20 | 24,789,496.13 | 5,270,738.93 | -19518757.2 | 0.21 | 71 |
| Sep-20 | 29,509,456.37 | 7,965,921.82 | -21543534.55 | 0.27 | 56 |
| Dec-20 | 31,644,067.34 | 10,444,263.34 | -21199804 | 0.33 | 45 |
| Mar-21 | 36,028,668.92 | 12,283,743.00 | -23744925.92 | 0.34 | 44 |
| Jun-21 | 40,547,701.29 | 13,200,867.44 | -27346833.85 | 0.33 | 46 |
| Sep-21 | 47,883,299.31 | 14,214,514.03 | -33668785.28 | 0.30 | 51 |
| Dec-21 | 47,883,299.31 | 14,214,514.03 | -33668785.28 | 0.30 | 51 |
| Mar-22 | 52,453,878.65 |  |  |  |  |
| Jun-22 | 53,320,363.27 |  |  |  |  |