Additional file 2.

| Name of the strategy (CFIR) | CFIR definition of the strategy | Actors | Action | Targets | Temporality | Dose | Implementation outcome affected | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase I |  |  |  |  |  |  |  |  |
| Identify and prepare champions | Identify and prepare individuals who dedicate themselves to supporting, marketing, and driving through an implementation, overcoming indifference or resistance that the intervention may provoke in an organization. | The research team | Local champions were identified for each involved healthcare profession | ED, PTs, GPs | Preparation phase | At least one local champion in each profession. | Reach, Adoption | Local champions have a positive impact on clinician behaviour change and help promote awareness (30). |
| Assess for readiness and identify barriers and facilitators | Assess various aspects of an organization to determine its degree of readiness to implement and identify barriers that may impede implementation and strengths that can be leveraged to facilitate the implementation effort. | The research team | Use results of the pilot study to improve readiness, facilitators and counter barriers. | Patients, ED, PTs, GPs | Preparation Phase | - | Implementation, Maintenance | Reducing the number of barriers improves the chances of successful adoption (31). |
|  |  | The research team | Evaluate during Phase I which facilitators and barriers for the implementation or TFCP were encountered | Patients, ED, PTs, | During Phase I | Often during the first months | Reach, Adoption, Implementation, Maintenance |  |
|  |  | The research team | Evaluate after Phase I which facilitators and barriers for the implementation or TFCP were encountered | Patients, ED, PTs, GPs | After Phase I | Once with those active in Phase I | Reach, Adoption, Implementation, Maintenance |  |
| Promote adaptability | Identify the ways a clinical innovation can be tailored to meet local needs and clarify which elements of the innovation must be maintained to preserve fidelity | The research team | Adapt processes or materials within the TFCP to the needs from participants or healthcare professionals | Patients, ED, PTs, GPs | During Phase I | As much as necessary | Reach, Adoption, Implementation, Maintenance | Adoption is a critical aspect to improve the appropriateness or contextual fit of an innovation (32). |
| Alter incentive/allowance structures | Work to incentivize the adoption and implementation of the clinical innovation | The research team | Set incentive team targets for ED doctors and nurses, when the targets are achieved the department receives a small reward. | ED | During Phase I | Once | Reach | Rewards can be used as motivational techniques (33). |
|  |  | The research team | Set an individual incentive award, the ED doctor or nurse with the most informed patients receives a reward. | ED | At the end of Phase I | Once | Reach |  |
|  |  | The research team | Provide financial resource for the PTs as regular care does not provide this | PTs | During Phase I | For each fall risk assessment | Reach, Adoption, Implementation. | Innovations need to have adequate financial resources (34, 35) |
| Conduct educational meetings | Hold meetings targeted toward educating multiple stakeholder groups (i.e. providers, administrators, other organizational stakeholders, community members, patients/consumers, families) about the clinical innovation and/or its implementation. | The research team | Attend the shift handover of ED doctors to educate them about their role in the TFCP | ED doctors | Preparation Phase and during Phase I | 19 times | Reach, Adoption | Educational interventions can improve beliefs and attitudes about evidence based practices in acute care (36). |
|  |  | The research team | Create material to increase awareness of the TFCP | ED, GP | Preparation Phase, Phase I | 9 times | Reach, Adoption |  |
|  |  | The research team | Use the clinical lessons for ED nurses to educate them about their role in the TFCP | ED nurses | Preparation Phase and during Phase I | 5 times | Reach, Adoption |  |
|  |  | The research team | Provide the PTs with an e-learning on the fall risk assessments | PTs | Preparation Phase | 1 time | Implementation | PTs may have a knowledge gap when it comes to using fall risk assessments (37). Providing education can help improve their understanding (35). |
|  |  | The research team | Conduct meetings to educate the PTs on the TFCP and the fall risk assessment | PTs | Preparation Phase and during Phase I | Two sessions | Implementation |  |
|  |  | The research team | Conduct two Q&A’s for PTs with questions on the TFCP or fall risk assessments | PTs | During Phase I | Two sessions | Implementation |  |
| Phase II |  |  |  |  |  |  |  |  |
| Promote adaptability | Identify the ways a clinical innovation can be tailored to meet local needs and clarify which elements of the innovation must be maintained to preserve fidelity | The research team and EHR support | Construct feasible transmural communication | ED | During Phase II | - | Reach | During Phase I, only a small percentage of the patients contacted the PTs. If contact details are provided, PTs may directly contact the patients. |
|  |  | The research team and EHR support | Construct reminder for TFCP in the electronic patient file | ED | During Phase II | - | Reach | Although the ED personnel were familiar with the TFCP, they did not consider it at the appropriate time, resulting in a low reach percentage. Reminders in the electronic patient file can be a trigger. |
|  |  | The research team and fall risk assessment software team | Construct a shorter fall risk assessment | PTs | Phase II | - | Implementation | A shorter fall risk assessment will leave more time for PTs to discuss the plan of multidomain interventions within the same visit. |
| Identify and prepare champions | Identify and prepare individuals who dedicate themselves to supporting, marketing, and driving through an implementation, overcoming indifference or resistance that the intervention may provoke in an organization. | The research team | Increase the number of local champions at the ED | ED | Phase II | At least one additional local ED champion | Reach, Adoption | Local champions have a positive impact on clinician behaviour change and help promote awareness (30). |
| Access new funding | Access new or existing money to facilitate the implementation | The research team and government? | Find sustainable financial resources for the PTs to conduct fall risk assessments | PTs | Phase II | - | Implementation | Limited and fragmented funding is a critical barrier to implementation (38). |
| Assess for readiness and identify facilitators and barriers | Assess various aspects of an organization to determine its degree of readiness to implement and identify barriers that may impede implementation and strengths that can be leveraged to facilitate the implementation effort. | The research team | Evaluate during Phase II which facilitators and barriers for the implementation or TFCP were encountered | ED, PTs, | During Phase II | Often during the first months | Reach, Adoption, Implementation, Maintenance | Reducing the number of barriers improves the chances of successful adoption (31). |
|  |  | The research team | Evaluate after Phase II which facilitators and barriers for the implementation or TFCP were encountered | Patients, ED, PTs, GPs | After Phase II | Once with those active in Phase II | Reach, Adoption, Implementation, Maintenance |  |
|  |  | The research team | Implement a reminding system for missed patients | ED | During Phase II | During Phase II after all missed patients | Reach, Adoption | ED doctors recommended sending a reminder by mail when a patient is missed to increase awareness in similar future cases. |
| Conduct educational meetings | Hold meetings targeted toward educating multiple stakeholder groups (i.e. providers, administrators, other organizational stakeholders, community members, patients/consumers, families) about the clinical innovation and/or its implementation. | The research team | Attend the shift handover of ED doctors to educate about their role in the TFCP | ED doctors | During Phase II | 15 times | Reach, Adoption | Educational interventions can improve beliefs and attitudes about evidence based practices in acute care (36). |
|  |  | The research team | Use the clinical lessons for ED nurses to educate them about their role in the TFCP | ED nurses | During Phase II | 6 times | Reach, Adoption |  |
|  |  | The research team | Create material to increase awareness of the TFCP | ED | Phase II | 10 times | Reach, Adoption |  |
|  |  | The research team | Implement the TFCP in the information provided to new ED doctors and nurses. | ED doctors and ED nurses | Phase II | - | Maintenance | New employees are informed of the TFCP's existence during their introduction, ensuring they are, at least somewhat, aware of it. |
|  |  | The research team | Provide the new PTs with an e-learning on the fall risk assessments. | New PTs | Phase II | 1 time | Implementation | PTs may have a knowledge gap when it comes to using fall risk assessments (37). Providing education can help improve their understanding (35). |
|  |  | The research team | Conduct meetings to educate the new PTs on the TFCP and the fall risk assessment. | New PTs | Preparation Phase and during Phase I | Two sessions | Implementation |  |
|  |  | The research team | Conduct a meeting with the “old” PTs to learn from each other’s experiences. | “Old” PTs | Phase II | One session | Implementation |  |
| After Phase II |  |  |  |  |  |  |  |  |
| Access new funding | Access new or existing money to facilitate the implementation | Insurance companies | Provide reimbursement for TFCP’s fall risk assessments. | PTs | After Phase II | - | Implementation | Reimbursement is necessary to cover the costs of care; excluding EBPs from fee-for-service lists/formularies disincentivises their use (38). |
| Promote adaptability | Identify the ways a clinical innovation can be tailored to meet local needs and clarify which elements of the innovation must be maintained to preserve fidelity | The research team and EHR support | Construct feasible transmural communication | ED | After Phase II | - | Reach | During Phase II, the transmural referral letters did not work optimal. Although it did show promising results, a sustainable alternative must be developed. |
|  |  | The research team and EHR support | Construct reminder for TFCP in the electronic patient file | ED | After Phase II | - | Reach | Construction of the reminder only focussed on ED nurses and was often ignored. |
|  |  | The research team and EHR support | Construct a SmartPhrase that automatically appear in the discharge letter. | ED | After Phase II | - | Implementation | In Phase I, an ED doctor indicated that the SmartPhrase could be easily forgotten in the future. An automatic SmartPhrase can’t be forgotten. |