| Table S1. Example of how implementation strategies were tracked in one month at a HIV testing site |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation strategy | What barriers does this strategy address? | What activity(ies) will be done? Provide a detailed description | Who will directly conduct and involve in the strategy - Role, name(s)ˠ | Dose | Temporality | August, 2020 |  |
|  |  |  |  |  |  | Implemented or not* (Y/N/R/C) | Summary of implementation, modifications, barriers and facilitators of implementation strategies |  |
| Involve executive boards | Lack of coordination among departments at the site | Provide information on the activities of the SNaP study to the Director Board of the district health center (DHC) | Vice Director of the Diseases and HIV/AIDS Control Department (Mr N) Psychosocial counselor (PC) (Ms P) | Once | At the beginning of SNaP implementation | Y | The system navigator (SN) and PC reported study activities to the site leader and representatives of different departments in the DHC during the periodic meetings of the organizations in early July. In general, the site leaders supported and created advantageous conditions for study implementation. |  |
| Conduct educational meetings | Low number of health staff at DHC | Inform the related departments of the DHC about activities of SNaP study, particularly the inclusion criteria of people who inject drugs (PWID) participants to be eligible to get the intervention | Vice Director of the Diseases and HIV/AIDS Control Department (Mr N) SN (Ms T) and PC (Ms P) | Once | At the beginning of SNaP implementation | Y |  |  |
| Assess and re-design workflow | Staff (SN and PC) are responsible for many tasks at the same time | Develop action plans on a weekly/monthly basis and inform heads of their departments about the plans | SN (Ms T) and PC (Ms P) | Once a week | After SNaP is implemented | Y | Plan for conducting study activities was embedded to the plan of the departments that the SN and PC were working for. This plan was developed on a weekly basis. |  |
| Develop educational materials | Steps of the required counseling session are not flexible | The PC spends time to review the intervention manual and sample video of the required counseling session | SN (Ms T) and PC (Ms P) | Once a month | After SNaP is implemented | Y | The SN and PC spent time reviewing intervention manual and video of the sample required counseling session. After finishing a counseling session with the first participant, the PC carefully listened to the recording file and discussed among their team to share lessons learnt and experiences. They also tried to spend time to discuss among their team on counseling skills once a month. |  |
| Organize clinician implementation team meetings | Steps of the required counseling session are not flexible | The PC uses the checklist of the required counseling sessions, which are included in the training materials. | SN (Ms T) and PC (Ms P) | As needed | After SNaP is implemented | Y | The PC shared with other team members that she had some difficulties to cover all information of the required counseling session with participants in the last month. For example, it was the end of the working hours at DHC and the participant wanted to be referred to the out-patient clinic (OPC) as soon as possible. The summary step of the required counseling session was missed but she perceived that all key information had been discussed with the participant before he was enrolled in HIV treatment. She reminded the participant that he could come back to get more counseling sessions in the coming time since the OPC was also located in this site. |  |
|  |  | Increase learning and experience among staff by discussion on the counseling sessions. |  |  |  |  |  |  |
| Revise professional roles | The system navigation and counseling sessions could be interrupted (if the SN and PC have to perform other tasks at the departments at the same time) | When the participants present at the DHC, the SN and PC inform their managers to assign other persons to perform the SN/PC’s tasks. | SN (Ms T) and PC (Ms P) | As needed | After SNaP is implemented | N | Since the SN and PC did not need help in the last month, this strategy was not implemented. |  |
| Revise professional roles | Miscommunication between the PC and clients, who are not influent in popular Kinh language | Use other translators (i.e. relatives of participants or other health workers) to communicate about SNaP study with participants, who are not influent in popular language. | SN (Ms T) and PC (Ms P) | As needed | After SNaP is implemented | N | It was not necessary to conduct since the first participant could communicate in the popular Kinh language. |  |
| Involve executive boards | Leaders of DHC lack of information on progress of SNaP study at their site. | Prepare and submit monthly reports to the director board | Vice Director of the Diseases and HIV/AIDS Control Department (Mr N) SN (Ms T) and PC (Ms P) | Once a month | After SNaP is implemented | Y | Report of the study progress was sent to the site leader on the first week of each month. The SN and PC reported and sent the implementation plan to the site leaders at the beginning of the study. They also reported the study progress to the site leaders during their weekly office meetings. |  |
| (*) Y: Yes; N: No; R: Removed; C: Completed (ˠ) Names of staff are abbreviated Note: DHC: district health center; OPC: out-patient clinic; PC: psychosocial counselor; SN: system navigator |  |  |  |  |  |  |  |  |