Table S1: Study Schedule and Milestones
	STUDY PERIOD
	Pre-Allocation
	Post-Allocation

	
	Enrolment
	Allocation
	Baseline 
	 Follow-Up
	Close-out

	TIME POINT
	0
	0
	0
	2 months
	6 months

	ENROLMENT
	 x
	 
	 
	 
	 

	Eligibility screen
	x
	 
	 
	 
	 

	Informed consent
	x
	 
	 
	 
	 

	Allocation
	 
	x
	 
	 
	 

	INTERVENTION (eFASH)
	 
	 
	 
	 
	 

	Intervention Group
	 
	 
	x
	x
	x

	Control Group
	 
	 
	 
	 
	 

	ASSESSMENTS 
	 
	 
	 
	 
	 

	Baseline variables:
	 
	 
	 
	 
	 

	Age
	x
	 
	 
	 
	 

	sex
	x
	 
	 
	 
	 

	HIV-status
	x
	 
	 
	 
	 

	Medical history/symptoms
	x
	
	
	x
	x

	Physical examination
	x
	 
	 
	x 
	 x

	Blood Tests
	x
	 
	 
	 (x)
	(x) 

	Chest x-ray
	x
	 
	 
	(x) 
	(x)

	XpertMTB/RIF urine, sputum
	x
	 
	 
	 
	 

	Management and medication plan
	
	
	x
	x
	x

	Outcome variables:
	 
	 
	 
	 
	 

	Correct management
	 
	 
	 
	
	x

	Freedom of symptoms
	 
	 
	 
	x
	x

	Death
	 
	 
	 
	
	x

	Safety outcomes
	
	
	x
	x
	x


	9/2017-8/2018*
	Study year 1: September 2018-August 2019*
	Study year 2: September 2019-August 2020* 

	
Milestones: 
_Study protocol finalized
_Contracts/agreements signed
_Required approvals and authorizations (Ethikkommittee der Nord-und Zentralschweiz, IHI-RB Tanzania, NIMR, Tanzania)  
_Data management system ready
_QA/monitoring system ready
_Safety reporting system ready
_Study team trained
	
Milestones: 
1.9.2018*: First patient first visit, 
both study sites active


	
Milestones: 
31.02.2020*: Last patient included
31.8.2020*: Last follow-up, 
Database cleaned, Final analysis of endpoints

	
	Number of patients included after 6 months: 217
	
	Number of patients included after 18 months: 650
	

	
	Number of patients included after 12 months: 433
	
	


[bookmark: _GoBack]*Dates as planned initially

Table S2: Assumptions for sample size calculation

	
	
	Final diagnosis at 6 months
	Correct management

	
	
	Definite TB
	Probable TB
	No TB
	

	Presumptive diagnosis at baseline
	Control group
	
	
	
	

	
	Definite TB (and therefore treated*)
	35%
	0
	0
	35%

	
	Probable TB (and therefore treated*)
	0
	30%
	25%
	30%

	
	No TB (and therefore not treated*)
	0
	2%
	8%
	8%

	
	Total
	
	
	
	73%

	
	Intervention group
	
	
	
	

	
	Definite TB (and therefore treated*)
	35%
	0
	0
	35%

	
	Probable TB (and therefore treated*)
	0
	25%
	10%
	25%

	
	No TB (and therefore not treated*)
	0
	5%
	25%
	25%

	
	Total
	
	
	
	85%


Shaded cells show those with correct management. TB=tuberculosis. *Based on the treatment decision made within the first 48 hours after primary evaluation
