April – July 2013 (4 months)*

July 2013 – July 2015 (24 months)

December 2013 – May 2014 (6 months)

July 2013 – March 2014 (9 months)

Process

- Preparation of detailed protocol to evaluate the  national coordinated implementation

- Review of outcomes and feedback from participants (service users, DBT therapists)

- Continued refinement of implementation process following feedback review

- Meeting with National Office for Suicide Prevention to discuss funding opportunities

- Securing funding

- Recruitment and appointment of coordinating team

- Appointment of Steering Group Committee

- Consideration and identification of training application process

- Teams attend Intensive Training-Part I

- Following attendance at training, contact from coordinating team to support implementation in service and identify programme start date for all teams

- Implementation of first DBT programme delivery in services

- Informing clinicians and managers about upcoming training opportunity and potential for DBT implementation

- Orientation meeting with teams that had been selected to attend DBT training

- Mandatory meetings between coordinating team and management teams in areas where teams had been selected to attend DBT training

- Individual team site visits with coordinating team and clinicians identified to attend training

- Meeting with treatment developer, Prof. Linehan, and key stakeholders (e.g. service users, managers)

*Timeline pertains to year one of the National DBT Project

Flynn D, Kells M, Joyce M, Corcoran P, Gillespie C, Suarez C, Swales M, Arensman E. Innovations in Practice: Dialectical behaviour therapy for adolescents: multisite implementation and evaluation of a 16‐week programme in a public community mental health setting. Child and Adolescent Mental Health. 2019 Feb;24(1):76-83.