Additional File 4: Themes identified from the Phase 1 Evaluation survey with FFX project implementation partners

- What worked well with the FFX project and why?

- Collaboration with researchers/research organisations to enable implementation

- Central coordination by APPRISE (including organisation and conduct of regular project meetings with sites, provision of support through implementation, communication, and availability)

- Existing relationships between the Office of Health Protection (Commonwealth) and APPRISE/UoM research team

- Rapid adaptation of the WHO FFX protocol to be used

- Data governance arrangements

- National funding mechanism and support

- Jurisdiction specific models of implementation to address unique challenges at each site

- National data repository and REDCap collection platform

- Timely analysis and reporting providing unique insights into household transmission in Australia

- What didn’t work well with the FFX project and why?

- Differing ethical and legislative frameworks across jurisdictions for the collection and analysis of case and contact data

- Length and complexity of ethics and site-specific governance approval processes which impacted on ability to undertake research components

- Issues in set-up relating to swab accessibility, engagement with pathology providers or other jurisdiction specific issues

- Eligibility criteria too stringent, i.e., excluded if household spoke a language other than English

- Lack of national data collection system – bespoke solutions per site which led to some duplication of work for entry into national repository

- Storage of data and analysis within the virtual machine proved challenging

- Missed opportunity due to delayed start of implementation or delay in pivoting project objectives/methods

- Limited outputs and data – due to lack of eligible cases and differences in site participation/engagement

- Further information needed to be collected to reflect epidemiology of COVID-19 e.g., additional household exposures/measures and how they varied over time

- Limited capacity and resourcing in health departments

- Missed opportunities due to lack of active engagement from health departments or representatives

- Division into public health and research components led to lost opportunities and created some tensions

- Concerns for participants (e.g., confusion about the distinction between mandatory public health and research components)

- Lack of preparedness – untested systems and processes were hard to implement in multi-jurisdictional study for the first time in a pandemic

- What expectations did you have for the FFX project (with regards to implementation strategy and outputs) at the beginning of the project and how have these changed over time?

- The FFX project would deliver on classic FFX objectives and would provide early and rapid epidemiological insights, i.e., characterisation of clinical course of disease, local epidemiology

- Able to deliver local information on key knowledge gaps i.e., the relative contributions of adult and children to transmission within households

- Greater collaboration from all sites

- Became apparent that we wouldn’t have enough data to provide certainty on our estimates of key parameters

- The data would play a larger role to inform public health advice

- Relevance of original objectives/research questions waned over time - wasn’t useful given no large-scale community transmission and as information came in from other sources

- Became apparent over time that most outputs will be long-term and more academic

- There would be more and faster recruitment

- Shifting to a case study of FFX project implementation – learning how we can implement these studies

- The massive limitations /recruitment bias

- Realities of research recruitment

- Unable to contribute to research outputs

- More support in completing ethics and governance processes

- That data would be more accessible and shared in a more timely and collaborative manner

- To finalise an ethically approved protocol across participating sites

- Expectation of further development of protocols and processes before further established community transmission of COVID-19 to contribute to local/international knowledge and inform ongoing public health and immunisation strategies.

- Unsure of expectations given this was the first time implementing an FFX in Australia across multiple jurisdictions

- What value do you expect FFX to provide going forward in the partnership grant or in future FFX iterations?

- Additional analyses incorporating genomics and serology

- Opportunity to characterise impacts of prior immunity and vaccination on severity and transmissibility of emerging variants within household units in longitudinal study

- Understanding how the FFX platform can be adapted for use in First Nations communities

- Establishment of a research network within existing public health systems

- Further strengthen relationships between public health representatives and researchers

- Opportunity to conduct further multijurisdictional FFX or other related research studies in Australia

- Consolidating a process for the management and implementation of FFX studies

- Further develop surveillance systems and capacity at a national level to help understand the epidemiology of pathogens

- Clarity around jurisdiction specific legislation for the collection of data and biological specimens on cases and their contacts

- Developing a process to expedite ethics and governance approvals for future iterations

- Not much added value

- What are the key foundational components/arrangements to have prepared for next time? Consider how this would change for another FFX iteration for COVID-19 and for different diseases of pandemic potential (e.g., influenza, Ebola, MERS-CoV)

- Investments in national data infrastructure to assist with rapid data sharing

- Development of a unified data collection platform – separate system for emergency public health research to ease collection/transfer requirements

- Harmonisation of data fields

- Pre-specified communication channels and focal points

- Consider what activities and capabilities might be required for different types of pathogens (e.g., airborne, droplet, fomite, vector)

- Maintenance of existing data governance and sharing arrangements from current project

- Investment into data analytics capacity (including testing and development of code)

- Pre-established ethics and governance mechanisms/approvals that are agreed to by health departments and cover all study aspects under one pathway (via public health act or full ethics approval)

- Identification of potential research partners to support all jurisdictions and further development of this workforce

- Developed protocols and other FFX study documentation

- Inclusion of biobanking with a broad remit to cover all eventualities for an emerging pathogen

- Inclusion of additional data fields; screening log to understand selection biases, non-recruited households

- Aim to embed within public health work to avoid duplication and participant confusion, encourage timely identification of case

- Developed capacity and resourcing (at a national level) to be provided to states

- Clear buy-in from all implementation partners to help further develop these studies and to ensure importance and role of FFX is clear as a public health activity

- Further piloting and refinement of FFX protocols before the next pandemic (regular exercising)

- Pre-engagement of national bodies (CDNA/PHLN) to facilitate cross-jurisdictional information sharing and agreeing to study components for any given pathogen in context in real time and within capacity of existing systems

- Implementation plan including agreed options for funding structure and clear responsibilities for all involved

- Exploration of the way Australian investigators can contribute to design and implementation of similar studies in our region and part of our capacity building commitment

- Pre-agreed information sharing with WHO to enable our well-resourced country to contribute to global knowledge gain in real time

- Clarification of role of FFX studies in broader surveillance plans (national and jurisdictional level) for pandemic response

- Understanding the nature of a threat (pathogen) and public health response that would suggest an FFX type project would be able to provide rapid and high-quality pandemic intelligence

- Exploration of the way Australian investigators can contribute to design and implementation of similar studies in our region and part of our capacity building commitment

- Pre-agreed information sharing with WHO to enable our well-resourced country to contribute to global knowledge gain in real time