Additional file 1: Appendix Table S1. Districts visited for field visit checklists

Cameroon

Ngaoundéré Urbain

Ngaoundéré Rural

Djoungolo

New Bell

Bamenda

Ndop

Malantouen

Ambam

Lolodorf

Limbe

Muyuka

Chad

HSS-targeted Districts

Doba

Mao

N’Djamena

Pala

Control Districts

Bessao

Lere

Moussoro

Additional file 1: Appendix Table S2. Changes to Chad’s planned HSS activities, before and after reprogramming

| Original activity | Status after reprogramming |
| --- | --- |
| Health districts organization and management |  |
| Support the organization of micro-planning workshops in the 10 health districts (HD) | Eliminated |
| Organize 2 PAO validation and adoption workshops in the 10 HDs | Modified |
| Support the monitoring meetings for actions in the 10 HDs | Maintained |
| Organize quarterly HSS activities monitoring and control meetings at the central level | Maintained |
| Organize and external audit | Maintained |
| Support the annual PRDS review meetings for actions in 8 Health Delegations | Maintained |
| Organize 3 reviews (twice a year) of the PNDS at the central level | Modified |
| Provide the health centers selected in the 10 Districts with 100 motorcycles for the advanced strategies | Implemented prior to change |
| Acquire 20 motorcycles for HC | Maintained |
| Acquire 2 4x4 vehicles for the 2 HD whose vehicles are not functional (Bébedjia and Sarh) | Maintained |
| Support the organization of health activities in fixed, advanced and mobile strategies, including market days | Eliminated |
| Provide the central EPI with a truck to distribute consumables, tools, cold chains, drugs and EPI consumables | Eliminated |
| Organize quarterly integrated supervision missions at the level of the HDs and DSRs concerned | Maintained |
| Provide the central HSS coordination office and the EPI with two all-terrain supervision vehicles | Eliminated |
| Provide 6 central units, 8 DSRs and 10 DSs with computer and office equipment kits to enter and process the data | Implemented prior to change |
| Provide EPI supervisors in 8 Gavi HR with complete IT kits | Maintained |
| Train the members of the 8 DSR teams and of the 10 Districts in GESIS data and software management | Eliminated |
| Train the health committees in the 10 HDs | Eliminated |
| Identify and train the community health care workers in the Responsibility Zones | Eliminated |
| Organize monthly meetings to monitor the management committees and include the community health workers | Eliminated |
| Put in place communication media such as posters, image boxes, etc., in the 10 HDs | Eliminated |
| Management of essential drugs, medicinal products, and cold chain |  |
| Train drug and vaccine management staff locally in the 8 regions and the 10 districts | Eliminated |
| Provide the 8 regions concerned with drug management and EPI tools | Eliminated |
| Carry out integrated formative supervision every 3 months in management tools, drugs, child survival activities | Maintained |
| Acquire generic essential drugs for the 100 HC | Maintained |
| Ensure distribution of vaccines, consumables, communication material, and drugs in 8 HR | Maintained |
| Equip the central EPI and the three sub-national depots with four 40 m3 cold chambers each (Moundou, Abéché and Sarh) | Implemented prior to change |
| Install the EPI equipment that is acquired (cold chambers) | Maintained |
| Provide each of the 8 DSRs and the 10 district departments with one freezer each | Maintained |
| Provide the 8 DSRs and 10 district departments with one refrigerator each | Eliminated |
| Provide the 100 health centers with solar refrigerators | Modified |
| Provide drugs to the 100 HC | Maintained |
| Maintain the cold chain equipment | Maintained |
| Health care human resource capacity |  |
| Assign 100 more skilled staff to the 10 priority health districts | Eliminated |
| Collect and publish data on the effective presence of the 100 staff members in the 10 Districts | Eliminated |
| Reward staff members with good performance based on merit | Eliminated |
| Reproduce the EPI management tools and the integrated formative supervision tool | Eliminated |
| Organize two mid-level management training sessions for the District Management Teams in the 10 HD | Maintained |
| Train/retrain 118 health care workers from the different levels in EPI, FDD/IRA and PNC | Eliminated |

Additional file 1: Appendix Table S3a. Status of HSS implementation in Cameroon, October 2015

| Central level |  |  |
| --- | --- | --- |
| Area | Activities | Complete |
| Community engagement | Produce education materials on EPI (posters, leaflets, images, vaccination schedule) | Yes |
|  | Distribute education materials on EPI (posters, leaflets, images, vaccination schedule) | Yes |
|  | Produce & distribute documentary & advertising messages on vaccination on national radio | Yes |
|  | Produce & distribute documentary & advertising messages on vaccination on national television | Yes |
| Supervision | Organize the supervision of the EPI technical committee trainings in the regions | Yes |
| Leadership & governance | Prepare an EPI procedures handbook & financial management guidelines | No |
|  | Support monitoring of Gavi’s reprogrammed HSS & the management of resources by WHO & MOH based on performance-based financing | Yes |
| EPI data | Install 12 teleconference systems before the end of 2013 (one per regional delegation of health, MinSanté & CTG of EPI) | Yes |
| Regional level |  |  |
| Area | Activities | % of regions visited (N=7) |
| Community engagement | Produce education materials on EPI (posters, leaflets, images, vaccination schedule) | 71% |
|  | Distribute education materials on EPI (posters, leaflets, images, vaccination schedule) | 86% |
|  | Sign partnerships agreements with 4 radio community channels per region to disseminate messages about EPI | 71% |
| Supervision | Organize the supervision of the EPI technical committee trainings in the regions | 100% |
| Leadership & governance | Hold quarterly regional coordination meetings | 29% |
|  | Train the EPI 10 accountants in the use of TOMPRO management software | 71% |
|  | Prepare an EPI procedures handbook & financial management guidelines | — |
|  | Organize a semi-annual joint WHO-MinSanté financial audit on the management of financial resources in the regions | 71% |
| EPI data | Implement 4 DQS tools in at least 30% of health districts during surveillance in 2014 | 71% |
| District level |  |  |
| Area | Activities | % of districts visited (N=11) |
| Community engagement | Train 4 community members per health area in routine immunization, search of dropouts, and immunization sessions’ planning | 73% |
|  | Educate 5 women associations per health district on EPI | 45% |
|  | Sign partnership agreements with 1 community organization per district to educate populations on EPI | 55% |
| Service delivery | Offer a package of integrated services to remote populations on a quarterly basis | 64% |
|  | Organize intensified immunization activities in districts with the largest number of unvaccinated children | 83% |
| EPI logistics | Procure & distribute 10 vehicles to support supervision in priority districts | 17% |
|  | Train 50 office health chiefs in the preventive maintenance & repair of solar refrigerators | 100% |
| Supervision | Organize biannual integrated supervision in at least 80% of the districts | 55% |
|  | Organize supervision of integrated training every two months in at least 60% of health areas | 45% |
| Leadership & governance | Hold monthly meetings for coordination & integrated data review in all districts | 64% |
|  | Hold a meeting to prepare annual action plans in districts | 82% |
|  | Hold a micro-planning meeting in all of the district’s health facilities, with all health sector heads & community health chiefs | 55% |
|  | Conduct a monitoring session in at least 60% of the health areas | 64% |
| EPI data | Train at least 50% of district management teams on using the data quality self-assessment tool (DQS) | 89% |
|  | Implement 4 DQS tools in at least 30% of health districts during surveillance in 2014 | 44% |
|  | Monthly maintenance of phones in health areas | 0% |

Additional file 1: Appendix Table S3b. Status of HSS implementation in Chad, July 2015

| Central level |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Area | Activities |  | Question |  |  | Number |  |
| Monitoring & supervision | Provide HSS & EPI central coordination office with 2 off-road vehicles for supervision |  | How many all-terrain vehicles are there in the HSS central coordination office? |  |  | 2 vehicles |  |
| Cold chain | Equip the central EPI & the three subnational deposits with four cold rooms of 40 m3 each (Moundou, Abéché & Sarh districts) |  | How many 40 m3 cold room are there at the central level of the EPI? |  |  | 14 rooms |  |
|  |  |  | How many 40 m3 cold rooms are there at the subnational depots? |  |  | 11 rooms |  |
| Regional level |  |  |  |  |  |  |  |
| Area | Activities |  |  | Question |  |  | % of regions visited (N=3) |
| Planning & coordination: managerial & technical capabilities | Support the annual review meetings of the annual plan in 8 regional health delegations |  |  | Is there a plan for regional health development for this regional health delegation? |  |  | 100% |
| EPI data | Train 8 teams DRS & the DS 10 members in Health Information System (HIS) data & software management |  |  | Was there a training for regional staff on the collection & analysis of HIS data? |  |  | 100% |
| Manager capacity for drugs & vaccines | Train 8 DRS on managing medicines & EPI tools |  |  | Has the DRS EPI Manager received training? |  |  | 100% |
|  |  |  |  | Has the DRS medicines, vaccines & medical products supply chain manager received training? |  |  | 100% |
|  | Ensure the distribution within 8 regional health delegations in vaccines, consumables, hardware communication & essential generic medicines |  |  | Is your DRS regularly supplied with vaccines, essential medicines, & medical products from the central level? |  |  | 100% |
| Cold chain | Provide each of the 8 regional health delegations & 10 health districts with a freezer each |  |  | How many freezers are available at the regional level? |  |  | Mao: 10 freezers Pala: 2 freezers |
|  | Maintain the cold chain equipment |  |  | Does the cold chain receive regular routine maintenance? |  |  | 100% |
| Human resources | Reward the best performing health staff member & DRS |  |  | Are facility staff rewarded for their performance? |  |  | 33% |
| District level |  |  |  |  |  |  |  |
| Area | Activities | Question |  |  | % case districts visited (N=4) |  | % control districts visited (N=3) |
| Planning & coordination: managerial & technical capabilities | Support the organization of goal-setting workshops in 10 health districts (DS) | Was there a goal-setting workshop in this district? |  |  | 100% |  | 100% |
|  | Organizing 2 workshops for validation & adoption of the annual operational plan in 10 DS | Was there a workshop for validation & adoption of the annual operational plan in this district? |  |  | 50% |  | 33% |
|  | Support the organization’s health activities in fixed, advanced & mobile strategies | Is there a district plan for advanced & mobile strategies? |  |  | 75% |  | 100% |
|  | 2 intermediate management trainings for DS management teams | Did any staff attend mid-level management training? |  |  | 25% |  | 0% |
| EPI data | Provide 6 CPUs, 8 regional health delegations & 10 health districts with hardware to capture & process data | Have there been logistical improvements for data collection (e.g., purchase of computers or computer equipment)? |  |  | 100% |  | 100% |
|  | Train 8 teams DRS & the DS 10 members in Health Information System (HIS) data & software management | Were district-level staff trained on the collection & analysis of HIS data? |  |  | 75% |  | 66% |
| Cold chain | Provide each of the 8 regional health delegations & 10 health districts with a freezer each | How many freezers are available at the district level? |  |  | Mao: 2 N’Djamena: 2 Doba: 1 |  | Bessao: 0 1st: 2 Moussoro: 0 |
|  | Maintain the cold chain equipment | Does the cold chain receive regular routine maintenance? |  |  | 100% |  | 66% |
| Human resources | Reward the best performing health staff member & DRS | Are facility staff rewarded for their performance? |  |  | 25% |  | 0% |
|  | Train 118 health workers at all levels in EPI & prenatal care | Has there been an EPI training for the staff? |  |  | 100% |  | 100% |

Additional file 1: Appendix Table S4. Results from the Root Cause Analysis organized by Consolidated Framework for Implementation Research (CFIR) domains and constructs

| Domain | Actor | Construct | Findings |
| --- | --- | --- | --- |
| Process | Gavi | Executing | Delayed disbursement of HSS funds |
|  |  | Reflecting and evaluating | Weak monitoring systems |
|  | Countries | Planning | Unrealistic implementation timelines |
|  |  | External change agents | Ineffective planning support from technical assistance partners |
|  |  | Formally appointed internal implementation leaders | Unprepared leadership (before and after reprogramming) |
|  |  | External change agents | Cameroon: HSS funds managed by WHO |
|  |  | Executing | Cameroon: HSS funds frozen |
|  |  | Executing | Chad: Blocked disbursements to districts |
| Inner Setting | Gavi | Structural characteristics | Slow internal Gavi procedures |
|  |  | Available resources | Inadequate francophone staffing |
|  |  | Networks and communication | Weak communication of realistic timelines |
|  |  | Networks and communication | Financial guidelines not communicated |
|  | Countries | Networks and communication | Weak communication to IRC during proposal process |
|  |  | Available resources | Lack of financial management tools |
|  |  | Networks and communication | Weak communication re: spending |
|  |  | Access to knowledge and information | Lack of institutional memory |
|  |  | Structural characteristics | Frequent staff turnover |
|  |  | Access to knowledge and information | Chad: Weak archiving |
|  |  | Culture | Chad: Lack of trust between central and district levels |
|  |  | Available resources | Cameroon: Strained human resources |
| Outer setting | Countries | External policy and incentives | Inflexible existing fiscal laws |
|  |  | Does not align with CFIR construct | Cameroon: Polio outbreak |