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	Activity
	Y1
	Y2
	Y3
	Y4
	Y5

	Development of detailed methodology for the study including tools for the data collection, piloting and post-piloting revisions as appropriate
	X
	
	
	
	

	Capacity building on use of realist evaluation and mixed methods research
	X
	
	
	
	

	Initial data collection and developing initial pathways(Step 1 in Figure 2)
	X
	X
	
	
	

	Validating pathways using IDIs and developing baseline variables for project
	X
	X
	
	
	

	Assessment of context, processes, outputs and outcomes of interventions, including sustainability of achieved changes (Step 2), including:
· Actors’ understanding and views about the programme and effects
· Programme outputs and outcomes, including their sustainability
· Views of users about the interventions and sustainability
· Programme costs and cost effectiveness 
· Effects of lobbying and advocacy on entrenching MCH on the agenda
	
	X
	X
	X
	

	Comparative analysis of findings from the three clusters, developing model and transferable best practices (Step 3)
	
	
	X
	X
	X

	Repeated engagement with national and international actors, to communicate results and discuss policy and practice implications 
	
	X
	X
	X
	X




