Supplemental File 3

Supplemental Table 1: Implementation Strategies and Targets by Condition

Supplemental Table 2: Actions for Implementation Strategies Organized by Phase and Condition

Table 1: Implementation Strategies and Targets by Condition

|  | ERIC Implementation Strategies | REP | TEAM | LEAD | TEAM + LEAD | Level & Target/Mechanism |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Develop educational materials | X | X | X | X | Individual: DOCC knowledge Self-efficacy Attitudes |
| 2 | Develop & organize quality monitoring systems | X | X | X | X |  |
| 3 | Conduct educational meetings | X | X | X | X |  |
| 4 | Distribute educational materials | X | X | X | X |  |
| 5 | Revise professional roles | X | X | X | X |  |
| 6 | Centralize technical assistance | X | X | X | X |  |
| 7 | Implementation facilitation |  | X | X | X | Practice: Adoption/sustainment (DOCC encounters, care competencies) |
| 8 | Assess for readiness/identify barriers & facilitators |  | X | X | X |  |
| 9 | Assess and redesign workflow |  | X | X | X |  |
| 10 | Promote adaptability |  | X | X | X |  |
| 11 | Purposely reexamine the implementation |  | X | X | X |  |
| 12 | Promote network weaving |  | X |  | X | Care Team: Affective, behavioral, & cognitive functioning Effectiveness |
| 13 | Organize clinician implementation team meetings |  | X |  | X |  |
| 14 | Conduct ongoing training |  | X |  | X | Individual: DOCC skill Fidelity |
| 15 | Provide ongoing consultation |  | X |  | X |  |
| 16 | Audit and feedback |  | X |  | X |  |
| 17 | Recruit, designate, and train for leadership |  |  | X | X | Practice: Implementation climate Implementation leadership |
| 18 | Identify and prepare champions |  |  | X | X |  |
| 19 | Make billing easier |  |  | X | X |  |
| 20 | Engage community resources |  |  | X | X |  |

Table 2: Actions for Implementation Strategies Organized by Phase and Condition

| REP Strategies: All Conditions |  |
| --- | --- |
| - Create project website with assessment portals, announcements, web training, and study updates (1, 4) |  |
| - Meet with practice leadership to introduce project (3) |  |
| - Create online training curriculum and platform with knowledge quizzes and performance feedback (1) - Create manuals for providers and caregivers (1) |  |
| - Develop patient registry infrastructure (2) |  |
| - Provide written materials describing team members’ roles, responsibilities, and functions (4, 5) |  |
| - Provide written materials describing patient registry infrastructure and functions (2, 4) - Train staff in CCM principles and DOCC workflows (3, 5) - Train staff in DOCC roles and responsibilities (3, 5) - Train staff in research participation requirements (3) |  |
| - Train staff in using patient registry infrastructure and functions (2, 3) - Provide physical and online intervention manuals (4) - Train staff in DOCC clinical content (3) - Conduct weekly calls to staff during training to solicit questions and address concerns (6) - Provide monthly open call-in consultation for general questions (6) |  |
| - Provide on-demand support and technical assistance to providers (6) |  |
| - Distribute monthly study newsletter with tips and updates (4) |  |
| Team Facilitation (TEAM) | Leadership Facilitation (LEAD) |
| Phase 1: Initiation and Goal-Setting - Schedule meetings (7, 13) - Create ground rules (13) - Build supportive relationships with team (7) - Assess/discuss provider and team-level barriers and facilitators (8) - Lead team goal-setting exercise (12) | Phase 1: Initiation and Goal-Setting - Schedule meetings (7) - Build supportive relationships with leaders (7) - Teach basics about DOCC (18) - Assess/discuss organization-level barriers and facilitators (8) - Set practice goals (17) |
| Phase 2: Role Clarification and Team Training - Clarify care team roles/tasks (9) - Map and revise workflows (9) - Teach communication & problem-solving skills (12) - Problem-solve implementation challenges (7) | Phase 2: Mentoring and Action Planning - Identify leader strengths (17) - Align DOCC implementation with practice priorities (18) - Reinforce leader attention to DOCC & support of its use (18) - Identify needed resources (e.g., space, time, technology) (7) - Create action plan to reach goals (17) - Problem-solve implementation challenges (7) |
| Phase 3: Coaching and Consultation - Teach/review DOCC content (14) - Review registry use and provide feedback (16) - Discuss case progress & treatment challenges (10, 15) - Provide treatment recommendations (15) - Adapt DOCC to meet practice needs (10) - Problem-solve implementation challenges (7) | Phase 3: Leveraging - Promote modeling and reinforcement of DOCC delivery (18) - Enhance community partner linkages (20) - Review and improve billing practices (19) - Adapt DOCC to meet practice needs (10) - Review/revise goals (11) - Problem-solve implementation challenges (7) |
| Phase 4: Sustaining - Lead structured team debriefings (11, 13) - Review/revise goals (11) - Create plan for sustainability and quality improvement (7, 11) - Problem-solve implementation challenges (7) | Phase 4: Marketing and Sustaining - Promote marketing/business care for DOCC (20) - Review lessons learned from other sites (20) - Create plan for sustainability and quality improvement (7, 11) - Update policies & procedures to enhance sustainability (17) - Review/revise goals (11) - Problem-solve implementation challenges (7) |

Note: Numbers in parentheses indicate the implementation strategy each action is associated with (see Table 1)