LIBERATE PROJECT TIMELINE

|  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity by Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
|  | Jan-Mar | Apr- Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr- Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr- Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr- Jun | Jul-Sep | Oct-Dec |
| Pre intervention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Canada approval |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics approval/renewal |  |  | X |  |  |  | X |  |  |  | X |  |  |  | X |  |
| CTA/Administrative approvals |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Intervention phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiate enrollment at pilot site |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Initiate enrollment at other sites |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Subject enrollment |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |
| Adverse event/SAE review |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |
| Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interim analysis |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Final analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| Publish manuscript |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |