Overview of all facilitating and impeding factors per (implementation) phase, including ranking scores

The factors presented in bold were added during the meeting with the NSF program coordinators.

Table 1: Phase 1 Program development: facilitating factors (n=12)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - The program matches the target group’s needs, wishes and possibilities | 1.1 | 1-2 |
| - The program is easy to implement locally | 3.8 | 2-7 |
| - Low threshold for participation of inactive people | 3.9 | 1-7 |
| - The program matches the needs, wishes and possibilities of sports clubs | 5.2 | 2-11 |
| - The program matches the NSF’s policy | 5.5 | 2-11 |
| - The program is fully developed; it is of good quality and ready to be implemented | 6.8 | 4-10 |
| - The NSF uses existing knowledge and experiences when developing the program | 7.3 | 3-10 |
| - The NSF collaborates with others when developing the program | 7.6 | 2-12 |
| - The (implementation of the) program (locally) is not costly | 7.8 | 3-12 |
| - The NSF runs pilot projects to test whether the program needs any adjustments | 9.1 | 4-12 |
| - The name of the program is appealing to the target group and sports clubs | 9.9 | 7-12 |
| - The program is offered in the same way everywhere | 10.0 | 6-12 |

Table 2: Phase 1 Program development: impeding factors (n=6)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - The program does not match the target group’s needs, wishes and/or possibilities | 1.8 | 1-6 |
| - The (implementation of the) program (locally) is costly | 3.2 | 1-5 |
| - The program does not match the needs, wishes and/or possibilities of sports clubs | 3.3 | 1-5 |
| - The program is not easy to implement locally | 3.8 | 2-6 |
| - The program (or parts of the program) is (are) not fully developed; it is not ready to be implemented | 4.0 | 2-6 |
| - The program consists of one (training) session or a one day event; in this way it is more difficult to capture participants’ interest for the sport/a sports club membership | 4.8 | 1-6 |

Table 3: Phase 2 Organizational (pre)conditions: facilitating factors (n=10)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - Having a “dedicated” program coordinator | 2.9 | 1-8 |
| - Sufficient time (in man-hours) to coordinate the program | 3.1 | 1-6 |
| - Internal support for the program | 3.9 | 1-9 |
| - Sufficient finances to coordinate and implement the program | 4.1 | 1-9 |
| - A good organizational structure for the program internally; tasks and responsibilities are properly assigned and clearly defined | 5.6 | 2-9 |
| - External support for the program | 5.8 | 2-10 |
| - Good external communication of the program | 6.9 | 4-9 |
| - Availability of trainer education and certification courses | 7.4 | 4-10 |
| - Good internal communication of the program | 7.5 | 4-10 |
| - Availability of implementation materials | 7.8 | 3-10 |

Table 4: Phase 2 Organizational (pre)conditions: impeding factors (n=3)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - Insufficient finances to coordinate and implement the program | 1.4 | 1-2 |
| - No or insufficient support for the program internally | 1.9 | 1-3 |
| - Internal organizational changes | 2.7 | 1-3 |

Table 5: Phase 3 Recruiting local sports clubs: facilitating factors (n=10)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - Providing a complete (readily usable) package to sports clubs | 3.8 | 1-7 |
| - Approaching sports clubs personally | 4.3 | 1-10 |
| - Support for the program by sports clubs | 4.7 | 1-10 |
| - A good promotion/marketing strategy | 4.8 | 1-8 |
| - Providing financial support to sports clubs | 4.8 | 1-10 |
| - Using a segmentation-based approach for recruiting sports clubs, based on expectations of successfulness | 5.3 | 1-9 |
| - Sufficient qualified trainers locally | 5.3 | 1-10 |
| - Evidence of effectiveness and/or benefits of the program can be provided to sports clubs | 6.5 | 2-10 |
| - Collaboration with others to promote the program and/or recruit sports clubs | 7.4 | 4-10 |
| - Absence of competing programs/sports | 7.9 | 3-10 |

Table 6: Phase 3 Recruiting local sports clubs: impeding factors (n=6)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - No or insufficient qualified trainers locally | 2.2 | 1-4 |
| - No or insufficient support for the program by sports clubs | 2.4 | 1-6 |
| - Unavailability of additional (local) funding possibilities | 3.6 | 1-6 |
| - No (proper) sports accommodation, location and/or facilities locally | 3.9 | 1-6 |
| - No collaboration with others to promote the program and/or recruit sports clubs | 4.2 | 2-6 |
| - Presence of competing programs/sports | 4.8 | 1-6 |

Table 7: Phase 4 Recruiting participants: facilitating factors (n=9)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - Support for the program by the target group | 3.3 | 1-6 |
| - A good promotion/marketing strategy nationally and locally | 3.4 | 1-8 |
| - The sports activities are organized in close proximity to the target group | 3.6 | 1-6 |
| - Sports clubs collaborate with other (local) parties to recruit participants | 4.1 | 1-9 |
| - Support of local promotion/marketing strategies by the NSF through provision of promotional materials and/or financial incentives | 4.1 | 2-8 |
| - The NSF collaborates with others to recruit participants | 5.1 | 2-8 |
| - The program reaches/engages inactive people | 6.2 | 2-9 |
| - Provision of sports equipment by the NSF or sports clubs at no (borrowing equipment) or low (hiring equipment) costs to facilitate participation | 7.3 | 3-9 |
| - Absence of competing programs or sports | 7.9 | 5-9 |

Table 8: Phase 4 Recruiting participants: impeding factors (n=7)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - The target group is unfamiliar with the program or the sport | 3.0 | 1-5 |
| - No or insufficient support for the program by the target group | 3.3 | 1-7 |
| - The program does not reach/engage inactive people | 3.4 | 1-5 |
| - The sports activities are not organized in close proximity to the target group | 3.7 | 1-6 |
| - Promotional/marketing materials and/or channels are not appropriate to the target group | 4.2 | 1-7 |
| - Participation in the program is costly | 4.4 | 2-7 |
| - Presence of competing programs or sports | 6.0 | 1-7 |

Table 9: Phase 5 Local implementation: facilitating factors (n=8)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - Enthusiastic people within sports clubs delivering (high-) quality performances | 2.9 | 1-7 |
| - Sports clubs are (personally) supported by the NSF when implementing the program locally | 3.8 | 1-7 |
| - Availability of follow-up sports activities locally that match participants’ needs, wishes and possibilities | 3.8 | 1-8 |
| - Personal/good communication between the NSF and sports clubs | 4.0 | 1-8 |
| - Enthusiastic participants; they stimulate both the sports clubs (to continue their efforts) as well as other participants | 4.2 | 1-8 |
| - A good organizational structure for the program locally; tasks and responsibilities are properly assigned and clearly defined | 4.8 | 1-7 |
| - Opportunities for sports clubs (provided by the NSF) to exchange knowledge and experiences | 5.9 | 2-8 |
| - Sports clubs collaborate with other (local) parties to run the program locally | 6.7 | 2-8 |

Table 10: Phase 5 Local implementation: impeding factors (n=5)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - No enthusiastic and/or incompetent people within sports clubs | 1.5 | 1-4 |
| - No clear division of roles, tasks and responsibilities between the NSF and sports clubs | 3.0 | 1-5 |
| - No (appropriate) follow-up sports activities for participants locally | 3.2 | 1-5 |
| - Insufficient personal contact between the NSF and sports clubs | 3.3 | 2-5 |
| - Sports clubs do not comply with the NSF’s implementation instructions and/or rules | 4.0 | 1-5 |

Table 11: Phase 6 Securing continuation of the program: facilitating factors (n=7)

| Facilitating factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - The program is part of the NSF’s long-term policy | 2.6 | 1-5 |
| - The NSF has sufficient financial resources available to continue the program/secure the program for the future | 2.7 | 1-6 |
| - The program is part of the sports club’s long-term policy | 3.0 | 1-6 |
| - Sports clubs have sufficient financial resources available to continue the program locally/secure the program for the future | 3.8 | 1-7 |
| - Evaluation of the program (and/or the implementation process) to identify necessary adjustments | 4.8 | 1-7 |
| - The NSF collaborates with others to continue the program/secure the program for the future | 5.5 | 2-7 |
| - Sports clubs collaborate with others to continue the program/secure the program for the future | 5.7 | 2-7 |

Table 12: Phase 6 Securing continuation of the program: impeding factors (n=2)

| Impeding factor | Mean ranking score | Range assigned rankings |
| --- | --- | --- |
| - The NSF has insufficient financial resources available to continue the program/secure the program for the future | 1.4 | 1-2 |
| - Sports clubs have insufficient financial resources available to continue the program locally/secure the program for the future | 1.6 | 1-2 |

Mean ranking score: For each factor: Sum of rankings divided by the number of program coordinators (n=12); Range assigned rankings: Lowest and highest ranking of factor.