Additional file 1. Timeline of all consecutive steps of the pilot study's preparation, ranging from concept to approval.

| Date | Phase | Action |
| --- | --- | --- |
| January 2023 | Conceptualisation & data discovery | Contacting EC Ghent (HIRUZ) to ask clarification on the coverage of the existing BELHES EC approval and ICF |
|  |  | First meeting with Sciensano’s DPO to explain the planned study and ask for advice |
|  |  | Contacting Sciensano’s legal office to ask advice regarding the recontacting of study participants |
|  | Realisation | Start drafting first version of the study protocol |
| February 2023 | Conceptualisation & data discovery + Realisation | Selecting variables from the BELHIS and BELHES 2018 database by consulting the codebook, and submitting a data request demand (with justification) to the HIS team |
| March 2023 | Realisation | First version of the Data Management Plan (DMPOnline) |
|  |  | March 9th 2023: First submission to the EC Ghent |
| April 2023 | Conceptualisation & data discovery | First meeting with BCR to discuss a potential data linkage study involving cancer registry data |
|  |  | First contact with Statbel to introduce a potential data linkage study involving Statbel data |
|  |  | First meeting with eHealth to discuss the data flow for a potential data linkage study |
|  | Realisation | April 5th 20243: Feedback from EC Ghent (HIRUZ) |
| May 2023 | Conceptualisation & data discovery | Meeting with EC Ghent (HIRUZ) to understand the best way forward (decision on the scope of the demand, e.g. prospective vs. retrospective data collection) |
|  | Realisation | Changed scope of the study (including data linkages with BCR and Statbel) and start drafting the second version of the study protocol |
|  |  | Start drafting the ISC demand |
| June – July 2023 | Conceptualisation & data discovery | Receiving feedback from the BCR on the study protocol and ISC demand |
|  |  | Second meeting with the BCR to discuss the study protocol, BCR codebook, ISC demand and further steps |
| August 2023 | Realisation | Sending ISC demand to Sciensano’s DPO |
| October 2023 | Conceptualisation & data discovery | Receiving feedback from the BCR on the study protocol and ISC demand |
|  |  | Second meeting with eHealth to discuss the data flow scheme |
|  |  | Receiving feedback from Statbel on the ISC demand |
|  |  | Contacts with the statistician of Statbel to finalize the list of selected variables |
|  |  | Receiving feedback from Sciensano’s DPO on the ISC demand and meeting to discuss next steps |
|  | Realisation | Finalising data flow scheme |
|  |  | Contacting IMA for the SCRA |
|  |  | Creation of the Processing Activity Assessment template by Sciensano’s DPO |
|  |  | Creation of the DPIA template by Sciensano’s DPO |
| November 2023 | Realisation | Submission of SCRA demand to the “SCRA pool” by IMA |
|  |  | Confirmation that the SCRA will be conducted by VIKZ |
|  |  | Final version of the Data Management Plan (DMPonline) |
|  |  | Final version of the Processing Activity Assessment |
|  |  | Start drafting the Microdata request form of Statbel |
| December 2023 | Realisation | 4th December 2023: submission to EC Ghent |
|  |  | Final version of the DPIA |
|  |  | Final version of the Microdata request form of Statbel (reviewed by DPO) |
| January 2024 | Realisation | Sending the Microdata request form and ISC demand to Statbel for informal approval |
|  |  | Sending the Microdata request form to Statbel’s DPO committee |
|  | Approval | 15th January 2024: Receiving approval from Statbel’s DPO committee |
|  |  | Statbel sends confidentiality contract to Sciensano |
|  |  | Informal approval for SCRA by VIKZ |
|  | Realisation | January 30th 2024: Submission to the ISC by Sciensano’s DPO |
| February – March 2024 | Realisation | February 13th 2024: Interview with the EC Ghent Review Committee |
|  |  | February 15th 2024: Additional questions from the EC Ghent – Reply on February 29th 2024 |
|  |  | February 28th 2024: Email with additional questions from the ISC – Reply the same day |
|  |  | March 15th 2024: Email with additional questions from the ISC – Reply on March 18th 2024 |
|  | Approval | March 19th 2024: Final approval by the EC |
| May – June 2024 | Approval | May 3rd 2024: Final approval by the ISC |
|  |  | May 22nd 2024: Sending draft DTA to the BCR |
|  |  | June 28th 2024: Confidentiality agreement with Statbel signed |
|  |  | June 28th 2024: Receiving revised DTA from BCR |
| August 2024 | Approval | August 29th 2024: Signed DTA with BCR |
| September – January 2025 | Approval | September 24th 2024: Draft TTP Global Document received from eHealth |
|  |  | January 11th 2025: Signed TTP Global Document |