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1. OBJECTIVE
To describe the procedures for the work to be carried out in the field by the teams to preparare sampling.
2. DEFINITIONS
Work team: Teams composed of 2 national programme technicians, 1 expatriate (coordinator or assistant) and a local supervisor. The technicians will also be trained to take biological samples (see corresponding SOP) and to fill in the different questionnaires.

There will be a total of 4 teams. Before starting the visits to the communities, a training day and a piloting of the survey will be carried out with these teams to ensure that all teams use common concepts and procedures.
3. IMPLEMENTATION DATE
· Drill: 24th and 25th October 2019.
· Training of teams: 11th November 2019.
· Survey piloting: 12th November 2019.
· Fieldwork: 12th November-6th December 2019.
4. PROCEDURES
Composition of the work teams
In total, it will be necessary to carry out the study:
· 2 field technicians.
· 1 supervisor.
· 1 coordinator.
· 1 driver.
Visits to the communities
· Arrival to the community.
· Meeting with the community leader.
· Identify and inspect the place where the work will be carried out (preferably health post/house of the word). Check that the place has:
· Roof (in case of rain).
· Good ventilation.
· Sufficient privacy for participants and technicians.
· Two tables (large enough to set up our workspace on).
· Chairs.
· Prepare the tables to distribute the material.
· Set up and check that all the necessary material is present:
· Tablecloth.
· Lancets.
· Alcohol for disinfection.
· Cotton wool.
· Gloves.
· Tropbio® filter paper discs.
· Material for drying filter paper discs: 7 mm rods  x 40-60 cm and Styrofoam or string and durable clips / clamps (for drying filter paper discs).
· Holders (with matte band and without matte band).
· Case for holders.
· Container for disposal of lancets.
· Sponge.
· Soakers. 
· Pre-printed bar-coded labels.
· 7x10 cm self-seal plastic bags with silicagel.
· Large resealable plastic bags to hold all Tropbio discs from the same province together (50-75 discs per bag).
· Permanent markers.

· Estimated working time:
· Each team will handle 30 participants from that community. The following procedures will be carried out:
1. Check that the participant meets the inclusion criteria.
2. Obtain informed consent.
3. While one technician obtains the samples, the other technician will conduct the survey.
· In a 9-hour day (7 hours of fieldwork + 2 hours of rest/travel) each team will survey and obtain samples from 60 participants (1 community). In total, 240 participants per day.

5. RELATED DOCUMENTS
· SOP_01_DAILY FIELD WORK_PLAN.
· SOP_02_WORK FIELD DAILY PLANNING.
· SOP_03_SURVEY CONDUCT.
· SOP_08_TAKING SAMPLES WHATMAN.
· SOP_09_TAKING SAMPLES THICK DROP.
· SOP_10_STORAGE AND SHIPPING SAMPLES.
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