Model of facilitator development

- Memorandum of Understanding developed between Macmillan Cancer Support and Health and Care Research Wales (who does what and how costs/ expenses are met)

- Trainee facilitators attend as delegates at a course delivered by an experienced facilitator

- Pre-course meeting with mentor (experienced facilitator), including going through the facilitator manual

- First course delivered, led by mentor with contributions from trainee facilitators

- Post-course feedback, evaluation and review

- Facilitator training day provided (for all new facilitators on the Health and Care Research Wales training programme)

- Second course delivered, led by mentor with contributions from 2 trainee facilitators (plus pre-/post- course meetings)

- Third / fourth course delivered – trainee facilitators fully co-facilitating and leading specific sessions (pre-/post-review)

- One-to-one meetings between facilitators and project lead to get feedback and assess any further training needs (interim report to Macmillan)

- Project review meeting with all three facilitators, Macmillan and Health and Care Research Wales

- Fifth course delivered – trainee facilitators leading the whole day (mentor observing)

- Final report to Macmillan

- Completion of facilitator training and certification

- Continuing course delivery without mentor (co-facilitation approach).