Time Prior to SbCST

- 6-8 months

- 3-4 months

- 2-3 months

- 1 week

1day – 1month

Post SbCST

Process

Simulation-based Clinical Systems Testing (SbCST)

Clinical Systems Activation Team Meeting (CSAT): stakeholder introduction to SbCST

Sim Med Dir. I Sim Dir. I Safety & Quality Dir. I Project Mgr. I Engineer I Construct Mgr.

Phase 1: PREPARATION

- Considerations Prior to and During Construction

- Tabletop I Tape on Floor I Cardboard Model I Virtual Reconstruction

CSAT : Touchbase

Phase 2: DEVELOPMENT

- Stakeholder Engagement

- Needs Assessment & Process Mapping

Anticipated Concerns: quality, medical directors, subject matter experts

Patient Safety

Process & Workflow

Standards of Care Goals

System Integration

Physical Space & Technology

- Objectives

- Scenario/Multi-patient Sim Scenarios/Front-line Staff Identification

- Simulation Preparation

Interprofessional Roster I Simulation Guides I Facilitators I HFMEA Planning

CSAT

QUALITY

LST Log

HFMEA

Latent Safety Threat Triage

Phase 3: IMPLEMENTATION

- Walkthrough with Stakeholders

- Run Scenarios in testing space

- SbCST

Prebrief I Sim I Modified PEARLS Debrief I

PDSA-informed Iteration: refine scenarios, clarify processes, address low-complexity LSTs, escalate high-complexity LSTs

CSAT

Phase 4: EVALUATION

- LST HFMEA scoring

- SEIPS classification of LSTs for work-system organization and response planning

- Report Completion and Follow Up Planning

Quality: create HFMEA summary report and recommendations

Leadership review for response planning and follow-up

Prioritized findings and recommendations prior to patient care

- Patient Move CSAT: SbCST Debrief