Supplementary Table 1. Project Milestone

| Activities | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |
| Initial focus group | X |  |  |  |  |  |  |  |  |  |  |
| PPHEA module development & delivery |  |  |  |  |  |  |  |  |  |  |  |
| Clinic A |  | X | X | X | X |  |  |  |  |  |  |
| Clinic B |  | X | X | X | X |  |  |  |  |  |  |
| Post-module survey (reaction) |  | X | X | X | X |  |  |  |  |  |  |
| Post-module survey (perception of innovation) |  | X |  |  | X |  |  |  |  |  |  |
| Post-PPHEA facilitation monthly meeting |  |  |  |  |  |  |  |  |  |  |  |
| Clinic A |  |  |  |  |  |  |  | X | X | X | X |
| Clinic B |  |  |  |  |  | X | X | X | X | X | X |
| EBI implementation |  |  |  |  |  |  |  |  |  |  |  |
| Clinic A (Small media + Reminder) |  |  |  |  |  |  |  | X | X | X | X |
| Clinic B (Flu-CRC) |  |  |  |  |  | X | X |  |  | X | X |
| Outcome data collection |  |  |  |  |  |  |  | X |  |  | X |