Supplemental online-only materials

Roseen EJ, Natrakul A, Kim B, Broder-Fingert S. Process mapping with failure mode and effects analysis to identify determinants of implementation in healthcare settings: a guide. Implementation science communications. 2024

Supplemental file 1: Literature review of prior studies using process mapping with FMEA

Supplemental Table 1. Characteristics of select studies

Supplemental file 2: Case studies of process mapping with FMEA

Supplemental Table 2. Overview of fourteen-step methodology with examples from cases

Supplemental file 1: Literature review of prior studies using process mapping with FMEA

Search strategy. Our PubMed search (fmea or failure mode and map) yielded 721 articles through January of 2024. We excluded studies that did not present a process map or FMEA. This search captured 51 articles with three additional manuscripts found through handsearching1-3 of relevant articles (total of 54 articles identified). We present 38 of the 54 articles in Supplemental Table 1. These 38 (70%) were selected for their vivid description of process mapping and FMEA within a healthcare setting. From each article we have extracted information on their: 1) research aim; 2) the general reason for use of process mapping and FMEA; 3) the number of clinics or health systems; 4) the types of stakeholders engaged; 5) whether a framework was used; 6) and whether the study was characterized as quality improvement or implementation science.

| Supplemental Table 1. Characteristics of select studies |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Author Year | Research aim | Use of process mapping and FMEA | Number of clinics or health systems | Stakeholders engaged | Framework | Quality improvement or implementation science* |
| Anthony et al.,1 2005 | To better understand the discharge process by investigating errors, to provide a generalizable model for investigating other patient safety issues | Evaluation of the hospital discharge process | 1 medical center in Boston | Working group which includes a nurse manager, administrative staff, health services researcher, statistician, substance abuse counselor, pharmacists, inpatient team directors, and research assistant | Donabedian’s framework | Quality improvement with the goal of implementation of a new discharge process |
| Babiker et al.,4 2018 | To improve clinical practice guideline implementation in the Middle East | Evaluation of the clinical practice guideline cycle | 1 university hospital in Riyadh, Saudi Arabia | 7 stakeholder members of an interdisciplinary team (trained in patient care, FMEA and clinical practice guideline methodologies, implementation science and quality improvement) | None | Quality improvement to mitigate risk |
| Broder-Fingert et al.,2 2019 | To identify the potential failures in implementing Family Navigation for children with autism spectrum disorder | Evaluation of a health service | 14 clinics and health centers across 3 states | 12 key stakeholders (included Family Navigators, study coordinators, research assistants, developmental and behavioral pediatricians, and study investigators) | CFIR | Implementation science |
| Cantone et al.,5 2013 | To evaluate patient safety in proton beam radiotherapy and to find risk mitigation strategies | Evaluation of a clinical intervention | 1 health center in Italy | Team of experts across institutions and disciplines in medical physics, radiation oncology, and risk management | None | Quality improvement to mitigate risk |
| Chilakamarri et al.,6 2021 | To identify potential failures in the inter-hospital transitions of neurocritical patients, to reduce communication failures and to enhance patient safety by implementing an action plan | Evaluation of an inter-hospital transfer process | 1 comprehensive stroke center including a multi-center academic health system | Multidisciplinary team of leaders (from the transfer coordination center, emergency medicine, neurocritical care), research nurse with experience in process mapping, healthcare providers and administrative staff | None | Quality improvement to mitigate risk |
| Daniels et al.,7 2015 | To analyze the processes that cause elevated International Normalized Ratios (INRs) in patients on warfarin while they receive antimicrobial therapy | Evaluation of a clinical intervention | 1 tertiary medical center | Multidisciplinary team that included physicians, pharmacists, and a systems analyst | None | Quality improvement to mitigate risk |
| Denny et al.,8 2014 | To analyze hazards in the process of delivering radiation therapy in an oncology setting and to implement risk-reducing actions in areas targeted for performance improvement | Evaluation of a clinical intervention, evaluation of implemented action plans | Network of 4 oncology hospitals | Site champion responsible for project oversight at each hospital, site-specific teams consisting of quality director, radiation oncologist, radiation therapist, physicist, dosimetrist, director of radiation therapy, patient safety officer/risk manager | None | Quality improvement to mitigate risk |
| Ford et al.,9 2009 | To evaluate the safety and reliability of a radiation beam therapy and to consider process improvement options | Evaluation of a clinical intervention | 1 radiation oncology clinic | 11-member committee of radiation oncology department staff plus staff from the center for innovation in quality patient care, with additional teams specific to each part of the process | None | Quality improvement to mitigate risk |
| Frewen et al.,10 2018 | To assess the risks of a newly paperless workflow in a radiation oncology department | Evaluation of a health service | 1 hospital in Australia | Team of radiation therapists and radiation oncologists | None | Quality improvement to mitigate risk |
| Gates et al.11, 2023 | To assess the risks of intravascular brachytherapy (IVBT) and identify appropriate quality assurance methods | Evaluation of a clinical intervention | 3 institutions that regularly perform IVBT | Multidisciplinary team with members from 3 institutions (included radiation oncologists, medical physicists, and cardiologists) | None | Quality improvement to mitigate risk |
| Gilmore & Rowbottom,12 2021 | To complete the routine risk assessment of a high-volume radiotherapy service at a UK hospital | Evaluation of a lung radiotherapy service | 1 UK NHS hospital | 7-member multidisciplinary team (2 oncologists, 2 physicists, 3 radiographers) plus a facilitator | None | Quality improvement to mitigate risk |
| Gray et al.,13 2023 | To evaluate the failure modes in the treatment process for volumetric-modulated arc therapy for total body irradiation (VMAT-TBI) and create a quality control program | Evaluation of a health service | 1 health institution | Multidisciplinary team of 3 physicians, 7 medical physicists, and 4 radiation therapists familiar with VMAT-TBI | None | Quality improvement to mitigate risk |
| Haroun et al.,14 2021 | To evaluate and make improvements to the process of blood sampling by nurses | Evaluation of a health service | 1 specialized cancer center | 7-member multidisciplinary team that included nurse manager, clinical nurses, quality coordinators, and a health informatics supervisor | None | Quality improvement to mitigate risk |
| Hosoya et al.,15 2015 | To examine the risks associated with poor adherence to ABL tyrosine kinase inhibitors | Evaluation of adherence to medication | 1 university hospital | 54 patients with chronic myeloid leukemia | None | Quality improvement to mitigate risk |
| Ibanez-Rosello et al.,16 2016 | To analyze the risks of the treatment process for Esteya, a device for electronic brachytherapy to treat skin cancer lesions | Evaluation of a health service | 1 health center | 7-member multidisciplinary team (including radiation oncologists and medical physicists) | None | Quality improvement to mitigate risk |
| Ibanez-Rosello et al.,17 2018 | To evaluate the risks of total skin electron irradiation (TSEI) and accordingly adapt quality assurance tools | Evaluation of a clinical intervention | 1 health center | 5-member multidisciplinary team (with representatives from the different steps of the process, e.g., radiation oncologists and medical physicists) | None | Quality improvement to mitigate risk |
| Intra et al.,18 2016 | To assess the risks of assisted reproductive technology and improve the process by targeting critical failure modes | Evaluation of a health service | 1 laboratory center for in vitro fertilization (IVF) | Team consisting of the laboratory director, 2 embryologists, 2 quality managers | None | Quality improvement to mitigate risk |
| Jones et al.,19 2015 | To evaluate the safety and feasibility of the new “STAT RAD” workflow for radiation therapy | Evaluation of a clinical workflow | 1 institution’s radiation oncology department | 11-member team familiar with STAT RAD (1 radiation oncology attending physician, 1 radiation oncology resident physician, 5 medical physicists, 1 dosimetrist, 1 medical student, 2 radiation therapists) | None | Quality improvement with the goal of implementing the STAT RAD workflow into clinic |
| Kim et al.,20 2019 | To evaluate the new magnetic resonance (MR)-only workflow compared to conventional workflow for planning external beam therapy of the pelvis | Evaluation of a health service | 1 health institution | 9-member multidisciplinary team (3 medical physicists, 2 radiation oncologists, 2 radiation therapists, 2 MR technologists) | None | Quality improvement to mitigate risk |
| Kisling et al.,21 2019 | To assess the risk of potential failures in the automated radiation planning assistant (RPA) and to assess risk reduction with implementing a targeted quality assurance program | Evaluation of a clinical intervention | 4 health centers in South Africa and Botswana | Team of 6 subject matter experts and 6 prospective users of RPA (medical physicists at the 4 centers) | None | Quality improvement to mitigate risk |
| Kricke et al.,22 2016 | To assess how the secondary use of electronic health record documentation may improve the discharge process from an inpatient cardiology unit | Evaluation of a health service | 1 hospital’s inpatient cardiology unit in Chicago, IL | Expert clinicians and staff from the inpatient cardiology unit (included the unit’s nurse educator and director) | None | Quality improvement to mitigate risk |
| Kunac & Reith,23 2005 | To assess the potential failures of medication usage in the neonatal intensive care unit (NICU) | Evaluation of a health service | 1 tertiary-level NICU in a New Zealand hospital | 8-member multidisciplinary team (4 management representatives of varying levels, 2 medical staff members, 1 nursing staff member, 1 pharmacy staff member) | None | Quality improvement to mitigate risk |
| Mattsson et al.,24 2019 | To assess the risks of oral antineoplastic treatment in an outpatient setting | Evaluation of a health service | 1 clinical oncology in Denmark | One team of healthcare professionals (nurses and physicians with diverse ages and expertise) and one team of cancer patients (with diverse backgrounds, identities, and diagnoses) | None | Quality improvement to mitigate risk |
| Manger et al.,25 2018 | To assess and improve the Xoft electronic skin brachytherapy process | Evaluation of a health service | 1 health clinic | 8-member multidisciplinary team (3 physicists, 2 dosimetrists, 1 physician, 2 therapists) | None | Quality improvement to mitigate risk |
| Nealon et al.,26 2022 | To evaluate the risks of the Radiation Planning Assistant (RPA), an automated radiation therapy contouring and planning tool | Evaluation of a health service | 1 health institution | Multidisciplinary team of RPA users (1 physician, 3 physicists, 1 dosimetrist), 2 RPA developers, 1 quality improvement representative | None | Quality improvement to mitigate risk |
| Nishioka et al.,27 2022 | To assess the risks of online magnetic resonance-guided adaptive radiotherapy and improve its quality assurance program | Evaluation of a clinical intervention | National Cancer Center Hospital (NCCH) in Japan | 14-member multidisciplinary team (2 radiation oncologists, 5 medical physicists, 5 radiation technologists, and 2 medical physics students) | None | Quality improvement to mitigate risk |
| Noel et al.,28 2014 | To assess risks specific to intensity-modulated adaptive radiotherapy compared to the standard intensity-modulated radiotherapy | Evaluation of a clinical intervention | NA | 4-member experienced team (2 clinical medical physicists, 1 clinical engineer, 1 radiation oncologist) | None | Quality improvement with the goal of clinical implementation of intensity-modulated adaptive radiotherapy |
| Prabhakaran et al.,3 2015 | To identify the failures in achieving the door-to-needle process in an hour or less for acute stroke at an academic versus community hospital | Evaluation of a clinical intervention | 2 hospitals in Chicago, IL (1 academic and 1 underserved community hospital) | 15-member multidisciplinary team (included stroke program coordinator, neurologists, radiologists, emergency medicine providers, pharmacists, and process improvement leader) from the academic hospital, and 8-member multidisciplinary team (included stroke program coordinator, lab supervisor, computed tomography supervisor, pharmacist, quality manager, and emergency medicine physician) from the community hospital | None | Quality improvement to mitigate risk |
| Rienzi et al.,29 2017 | To identify potential failures in the traceability process of gametes and embryos during IVF and to strategize for mitigating the risk of mismatches | Evaluation of a clinical intervention | 7 health centers in Italy (3 public and 4 private) | At least 49 stakeholders, in teams of 7+ members in each of the 7 health centers (included lab directors, quality control professionals, embryologists, gynecologists, nurses, administrators) | None | Quality improvement to mitigate risk |
| Schuller et al.,30 2017 | To use FMEA in a small, resource-limited community practice by evaluating the failure modes of their stereotactic radiosurgery program | Evaluation of a clinical intervention | 1 radiation oncology department of a small community practice | 8-member multidisciplinary team (including representatives from dosimetry, radiation therapy, nursing, research, administration staff, physicians, and physics) | None | Quality improvement to mitigate risk |
| Sorrentino31 2016 | To evaluate the risks of failures in emergency department handoff processes and to develop a standardized handoff for process improvement | Evaluation of a health service | 1 acute care hospital emergency department | Committee of 12 team members | Donabedian’s framework | Quality improvement to mitigate risk |
| Takemori et al.,32 2022 | To evaluate the risks of accelerator-based boron-neutron capture therapy (BNCT) needed for quality assurance | Evaluation of a clinical intervention | 1 hospital | 7-member multidisciplinary team of (1 physician, 1 nurse, 2 medical physicists, 3 radiologic technologists) | None | Quality improvement with the goal of clinical implementation of accelerator-based boron-neutron capture therapy |
| Teixeria et al.,33 2016 | To assess the risk profiles of different cancer centers for stereotactic radiosurgery programs in order to develop quality management programs | Evaluation of a clinical intervention | 3 radiotherapy cancer centers in Brazil | 8-13 member teams at each cancer center (included radiation oncologists, medical physicists, technologists, nurses) | None | Quality improvement to mitigate risk |
| Walsh et al.,34 2013 | To have parents of cancer patients identify the failures associated with pediatric home oral chemotherapy | Evaluation of a health service | 3 pediatric oncology clinics in the northeast and southeast | 4 parents at two of the sites and 10 parents at the third site | None | Quality improvement to mitigate risk |
| Xu A, et al.,35 2017 | To evaluate the risks of Gamma Knife radiosurgery, in order to eventually develop a quality assurance program for this treatment | Evaluation of a clinical intervention | 1 medical center | Multidisciplinary team (of medical physicists, radiation oncologists, neurosurgeons, nurses, safety officers, and schedulers) created the process tree and failure modes table. Another team (of medical physicists, 2 radiation oncologists, and 3 neurosurgeons familiar with Gamma Knife) scored the failure modes using FMEA | None | Quality improvement to mitigate risk |
| Xu Z, et al.,36 2019 | To identify and assess the failures that cause delay in the process of radiation therapy | Evaluation of a clinical intervention | 1 main health campus | Administrative staff and a group of physicists, therapists, dosimetrists, and physicians from the radiation oncology department | None | Quality improvement to mitigate risk |
| Yarmohammadian et al.,37 2014 | To evaluate the risks of processes carried out within the medical record department and how performance improvement of these processes could be achieved | Evaluation of a health service | 1 hospital | 13-member multidisciplinary team of key informants (clerks, coder, statistician, administrators) | None | Quality improvement to mitigate risk |
| Yousefinezhadi et al.,38 2016 | To assess potential failure modes in the ICUs of two different kinds of hospitals | Evaluation of a health service | 2 hospitals (1 non-governmental and 1 governmental) in Tehran | Multidisciplinary team (chief nurse, chief nurse assistant, nurse supervisors, head ICU nurse, bedside nurse, patient safety experts) at each hospital | Eindhoven Classification Model (ECM) | Quality improvement to mitigate risk |
| *This categorization of quality improvement (QI) or implementation science (IS) was determined through the following means: the authors self-identifying the purpose or design of their study as inherently QI or IS, the study using key words and terminologies specific to QI or IS, the study being published in a specifically QI or IS journal, the study using a framework known to be used for IS, such as the Consolidated Framework for Implementation Research (CFIR) |  |  |  |  |  |  |

Supplemental file 2: Case studies of process mapping with FMEA

Case studies

Two cases are described below and in Supplemental Table 2 to illustrate how process mapping with FMEA can be operationalized in implementation research. The principal investigators of the two cases followed similar guidance for design, so overlap was expected. However, we also highlight differences in the evidence-based practice, context of participating clinics, and operationalization of each phase and step in the methodology.

Case 1

Our first case explores referrals by primary care providers (PCPs) to chiropractic care for patients with low back pain. Chiropractic care is an evidence-based practice that is safe, effective, and recommended by the American College of Physicians as first-line care for low back pain.39,40 This mixed methods study sought to identify barriers to accessing chiropractic care in low-income, racially diverse communities who are less likely to report use of chiropractic care and other nonpharmacologic treatments for low back pain41.

Phase 1: Formulating a plan

Four stakeholder teams were formed to represent four primary care clinics, each consisting of PCPs, clinic staff, and chiropractors. Methods then consisted of the following phases: initial process mapping exercises via one-on-one meetings and final process map generation through iterative thematic analysis, FMEA workshops and surveys to evaluate process maps, and development of an implementation strategy to be evaluated in three community health centers.

Phase 2: Generating process maps

To ensure that each stakeholder has a clear understanding of the study, individuals were first presented with a brief overview of the context and goals of the research. A member of the research team (e.g., principal investigator) gave this initial presentation. During the process mapping exercise, the investigator used their electronic device to “screen-share” while taking basic notes, such that the stakeholder could observe how their data was recorded in real time. While the principal investigator visually categorized the main points of the stakeholder narrative within the map skeleton on their device, research assistants simultaneously generated comprehensive notes.

When subsequently categorizing elements of each stakeholder narrative, the factors deemed “failure modes” were first added to a process map skeleton of general nodes. Because failure modes are barriers and thus rated by FMEA, they were visually distinct from the general nodes. All general nodes were framed in the affirmative (e.g., PCP decides to initiate conversation about chiropractic care). Failure modes appeared as smaller boxes, aligned in an indented list below their respective subprocess node. All failure modes were described as actionable steps and framed in the negative; for example, “provider is not able to put a chiropractic referral into the electronic health record.”

Factors that were purely “facilitators” were then added to the process map as general nodes (which, at times, resulted in breaking down an existing subprocess into several general nodes) or as failure modes (which involved reframing language in the negative). For example, “patient meets with a financial counselor for an explanation of insurance benefits” is one such “facilitator.” This allowed investigators to shed light on unique narrative elements that would otherwise not be captured in the concise language of the process map.

Investigators compiled a cumulative list that included all barriers identified by stakeholders across all teams, which was then condensed into a shorter “priority” list based on feedback from site champion stakeholders. Because it was relevant to compare across different stakeholder groups, every participant in the FMEA rating process rated every barrier in this condensed list (see Prioritizing failure modes of Phase 3). Three members of the research team separately went through the list of barriers to ensure that each list item was indeed distinct. At times, the investigators combined what a stakeholder had originally described as two distinct barriers, e.g., if it was decided that one was the reason for the other.

Phase 3: FMEA

Brief FMEA workshops were conducted virtually to introduce the rating methodology to stakeholders before they completed an FMEA survey. This included inviting participants who helped generate process maps and other representatives of a participating clinic. When given an hour for workshop the time was roughly divided as follows: present and discuss the final process map (10 minutes), introduce FMEA (10 minutes), and have participants rate barriers with FMEA on REDCap, a secure online survey platform (40 minutes). A brief introduction to FMEA was also recorded so that stakeholders who could not attend the workshop would be able to complete the FMEA survey.  As part of introducing FMEA to the participants, rating guides were presented to describe the scoring system (e.g., how having the lowest occurrence score of 1 corresponded to minimal occurrence, meaning that it occurs in ≤1 in 10 patients eligible for chiropractic care). A survey link was first distributed to participants during the workshop so that it could be initiated in real time, but follow-up emails were sent to all team members after the workshop in order to encourage survey completion.

Phase 4: Devising an implementation strategy

Forthcoming FMEA results will be used to inform the development and tailoring of implementation strategies to increase referrals to chiropractic care for low back pain in three primary care clinics. The study team will present a final list of strategies to each clinic team and refine based on feedback. The FMEA survey created from initial clinics could be used to identify or prioritize barriers in additional clinics prior to implementation. Additional unique barriers in new clinics could be identified through additional map creation and/or meetings with stakeholders.

Case 2

Our second case involves implementation of a Family Navigation intervention for children with autism spectrum disorder. Family Navigation is an evidence-based practice to improve access to care. Family Navigation consists of an individual with “lived experience” providing both logistical and interpersonal support to families during a time-limited period of care needs.42 This mixed methods study was designed to understand barriers to implementing this practice across three large health systems. The investigation was embedded in a larger randomized controlled trial of Family Navigation, and thus supporting an overall hybrid type I trial design.43

Phase 1: Formulating a plan

Because this study was embedded in a larger trial, stakeholders consisted of all study staff: study/site principal investigators, family navigators, and research staff. Specifically, we interviewed 12 stakeholders: 3 family navigators, 3 study coordinators, 1 research assistant, 3 developmental and behavioral pediatricians, and 2 Principal or Co-investigators.

Phase 2: Generating process maps

Interviews were used to create a draft process map of family navigator implementation; stakeholders were given the opportunity to review and refine the map.

Phase 3: FMEA

After the process map was complete, we conducted an FMEA workshop to evaluate the process map. This consisted of a meeting with all stakeholders listed above to review the process map, introduce FMEA methods, and then conduct the FMEA. In the first part of the FMEA exercise, the principal investigator of the FMEA study distributed copies of the process map for all participants to review. Participants then had an opportunity to ask questions and discuss as a group. Once all questions were resolved, the PI presented two practice cases from the literature for the group to review as a means of better understanding the FMEA methodology. For each practice case, the group conducted a practice FMEA, identifying and rating each potential implementation failure.

After the practice cases, the group conducted the FMEA for family navigator implementation. Because the process map was complex (66 steps were included), the first step of the FMEA was to identify the most critical steps to evaluate in the FMEA. Using group consensus, seven steps emerged as “high priority”. Each stakeholder was then asked to rate these seven high-priority steps according to the FMEA methodology.

Phase 4: Devising an implementation strategy

Once the FMEA was completed, we used that data to design a trial (currently ongoing) to empirically test new implementation strategy components (PMID: 31842963). The data are also being used in a separate trial of family navigator implementation (R34MH120190).

| Supplemental Table 2. Overview of fourteen-step methodology with examples from cases |  |  |  |
| --- | --- | --- | --- |
| Recommendation | Description | Case Study 1 (K23-AT010487) | Case Study 2 (K23-MH109673)2 |
| Phase 1, Step 1: Choose a guiding framework | Decide on what kind of framework will inform the thematic analysis to identify determinants of implementation. | Investigators chose to use Consolidated Framework for Implementation Research (CFIR) as a guide for structuring process maps and conceptualizing future implementation strategies. A pilot interview study of a codebook using CFIR was performed at clinics participating in Case 1.44 |  |
| Phase 1, Step 2: Form teams | Decide if more than one type of stakeholder and more than one clinic site will be involved in building the process maps, which will inform the number of teams. Also decide how stakeholders will be grouped into these teams (e.g., by clinic or by type of stakeholder role). | Multiple stakeholder roles and multiple clinic sites were involved. All stakeholders were grouped broadly by geographic location (Massachusetts and Minnesota) and then more specifically by clinic site (Clinics 1 and 2 in Massachusetts and Clinics 1 and 2 in Minnesota). | Stakeholders included all staff participating in a research study. No additional stakeholders were included. Stakeholders were not grouped. |
| Phase 1, Step 3: Recruit stakeholders for process mapping | Use a sampling strategy to recruit the target number of stakeholders. | With facilitation from site champions, investigators used purposive sampling to recruit stakeholders in specific roles from each clinic site (e.g., 2-3 PCPs, 2-3 staff, 2 chiropractors). | Because this FMEA was embedded in an RCT, all staff of the trial were invited (and agreed to) participate. |
| Phase 2, Step 4: Conduct initial process map meetings | Researcher leads a one-on-one meeting with each individual stakeholder. Stakeholder details a complete narrative of the process, which may be guided by a process map skeleton of basic nodes. | Principal investigator led virtual meetings with individual stakeholders over Zoom. Investigator used the screen-share feature to display a process map skeleton of basic nodes to orient the stakeholder. Research assistants transcribed notes on the entirety of the stakeholder’s narrative. | Research assistant led one-on-one in person meetings with each stakeholder. Process map was displayed and discussed in real time. |
| Phase 2, Step 5: Create stakeholder narratives | Based on their respective process map meeting, generate basic narratives for each individual stakeholder. | Research assistants organized their transcribed notes and restructured them into individual narratives with emphasis on the unique factors described by each stakeholder. | No narratives were completed. |
| Phase 2, Step 6: Build a process map skeleton | Based on each individual stakeholder narrative, divide the narrative into distinct subprocesses. Use these subprocesses to visually build a process map skeleton. | Process map skeleton was formed by depicting subprocesses as text within blank white boxes. |  |
| Phase 2, Step 7: Incorporate factors into process map | Categorize the rest of the information in each stakeholder narrative as: “failure mode,” “facilitator,” or “other.” Decide if each process map should include all three of these types of factors, or if it should be limited to only depicting failure modes. Visually incorporate factors into the map skeleton to fill out the rest of the process map. | Only “failure modes” were visually incorporated into the process map; “facilitators” were edited to be framed as “failure modes” so that they could be included as well. Factors categorized as “other” were incorporated as text in a “Contextual Factors” box, located outside of the flow of the map. | All steps were incorporated into process map. |
| Phase 2, Step 8: Decide on consistent language and layout for the process maps | Ensure that all text is uniform for each type of object in the process map. Language and layout should be uniform across all subprocesses and all failure modes, for example. | All subprocess nodes were framed as positive actions with a clear actor (subject). All failure modes were framed as negative actions to clearly show how they would impede the process. |  |
| Phase 2, Step 9: Finalize process maps | Shared each finished process map with its respective stakeholder for member checking. Use thematic coding to create a cumulative list of determinants (e.g., failure modes). If applicable, coding can facilitate the consolidation of initial process maps into one combined process map per stakeholder team. | Process maps were coded to create a cumulative list of barriers across all four clinic sites. Investigators used Microsoft Excel to create this cumulative list and to visualize how the commonality of each barrier (e.g., to note which barriers were described by every stakeholder within a team compared to those described by only one stakeholder member within a team). | Process maps were coded to create a list of barriers. Investigators used Microsoft Excel to create this cumulative list and to visualize how the commonality of each barrier (e.g., to note which barriers were described by every stakeholder within a team compared to those described by only one stakeholder member within a team). |
| Phase 3, Step 10: Plan FMEA workshops | Decide on a point-scale for FMEA and create a rating guide. Decide how many barriers will be rated and which stakeholders will do the rating. | A 10-point scale was used, and a rating guide was created that provided study-specific definitions for each FMEA category of occurrence, detection, and severity (e.g., an occurrence score of 1 = occurs in less than 1 out of 10 patients with low back pain). All identified barriers were rated by every stakeholder type. The raters were not necessarily all the same stakeholders who had contributed to the initial process mapping. | A final process map was reviewed. Of the 66 steps, 7 were selected as “high-priority” using consensus methods. |
| Phase 3, Step 11: Conduct FMEA workshops | Provide stakeholders with rating guides and other materials such that they understand the goals of the study and their role with FMEA. | A 10-point scale was used, and a rating guide was created that provided study-specific definitions for each FMEA category of occurrence, detection, and severity. | A 10-point scale was used, and a rating guide was created that provided study-specific definitions for each FMEA category of occurrence, detection, and severity. |
| Phase 3, Step 12: Data Analysis | Run descriptive statistics to calculate | 70+ barriers to be rated by clinicians and staff at four primary care clinics | Presented in Broder-fingert2 |
| Phase 4, Step 13: Choose which barriers are to be addressed | Based on FMEA results, select identified barriers to target with implementation | Data forthcoming (K23-AT010487) | Presented in Broder-fingert2 |
| Phase 4, Step 14 Devise an implementation strategy | Either create an implementation strategy or modify an existing strategy that is tailored to selected barriers. | Data forthcoming (K23-AT010487) | Data are currently being used to test different implementation strategies. R34MH120190 |

Reference List

1.	Anthony D, Chetty VK, Kartha A, McKenna K, DePaoli MR, Jack B. Re-engineering the Hospital Discharge: An Example of a Multifaceted Process Evaluation. In: Henriksen K, Battles JB, Marks ES, Lewin DI, eds. Advances in Patient Safety: From Research to Implementation (Volume 2: Concepts and Methodology). Rockville (MD)2005.

2.	Broder-Fingert S, Qin S, Goupil J, et al. A mixed-methods process evaluation of Family Navigation implementation for autism spectrum disorder. Autism. 2019;23(5):1288-1299.

3.	Prabhakaran S, Khorzad R, Brown A, Nannicelli AP, Khare R, Holl JL. Academic-Community Hospital Comparison of Vulnerabilities in Door-to-Needle Process for Acute Ischemic Stroke. Circ Cardiovasc Qual Outcomes. 2015;8(6 Suppl 3):S148-154.

4.	Babiker A, Amer YS, Osman ME, et al. Failure Mode and Effect Analysis (FMEA) may enhance implementation of clinical practice guidelines: An experience from the Middle East. J Eval Clin Pract. 2018;24(1):206-211.

5.	Cantone MC, Ciocca M, Dionisi F, et al. Application of failure mode and effects analysis to treatment planning in scanned proton beam radiotherapy. Radiat Oncol. 2013;8:127.

6.	Chilakamarri P, Finn EB, Sather J, et al. Failure Mode and Effect Analysis: Engineering Safer Neurocritical Care Transitions. Neurocrit Care. 2021;35(1):232-240.

7.	Daniels LM, Barreto JN, Kuth JC, et al. Failure mode and effects analysis to reduce risk of anticoagulation levels above the target range during concurrent antimicrobial therapy. Am J Health Syst Pharm. 2015;72(14):1195-1203.

8.	Denny DS, Allen DK, Worthington N, Gupta D. The use of failure mode and effect analysis in a radiation oncology setting: the Cancer Treatment Centers of America experience. J Healthc Qual. 2014;36(1):18-28.

9.	Ford EC, Gaudette R, Myers L, et al. Evaluation of safety in a radiation oncology setting using failure mode and effects analysis. Int J Radiat Oncol Biol Phys. 2009;74(3):852-858.

10.	Frewen H, Brown E, Jenkins M, O'Donovan A. Failure mode and effects analysis in a paperless radiotherapy department. J Med Imaging Radiat Oncol. 2018;62(5):707-715.

11.	Gates EDH, Wallner K, Tiwana J, et al. Improved safety and quality in intravascular brachytherapy: A multi-institutional study using failure modes and effects analysis. Brachytherapy. 2023;22(6):779-789.

12.	Gilmore MDF, Rowbottom CG. Evaluation of failure modes and effect analysis for routine risk assessment of lung radiotherapy at a UK center. J Appl Clin Med Phys. 2021;22(5):36-47.

13.	Gray T, Antolak A, Ahmed S, et al. Implementing failure mode and effect analysis to improve the safety of volumetric modulated arc therapy for total body irradiation. Med Phys. 2023;50(7):4092-4104.

14.	Haroun A, Al-Ruzzieh MA, Hussien N, et al. Using Failure Mode and Effects Analysis in Improving Nursing Blood Sampling at an International Specialized Cancer Center. Asian Pac J Cancer Prev. 2021;22(4):1247-1254.

15.	Hosoya K, Mochinaga S, Emoto A, et al. Failure mode and effects analysis of medication adherence in patients with chronic myeloid leukemia. Int J Clin Oncol. 2015;20(6):1203-1210.

16.	Ibanez-Rosello B, Bautista-Ballesteros JA, Bonaque J, et al. Failure mode and effects analysis of skin electronic brachytherapy using Esteya((R)) unit. J Contemp Brachytherapy. 2016;8(6):518-524.

17.	Ibanez-Rosello B, Bautista JA, Bonaque J, et al. Failure modes and effects analysis of total skin electron irradiation technique. Clin Transl Oncol. 2018;20(3):330-365.

18.	Intra G, Alteri A, Corti L, et al. Application of failure mode and effect analysis in an assisted reproduction technology laboratory. Reprod Biomed Online. 2016;33(2):132-139.

19.	Jones RT, Handsfield L, Read PW, et al. Safety and feasibility of STAT RAD: Improvement of a novel rapid tomotherapy-based radiation therapy workflow by failure mode and effects analysis. Pract Radiat Oncol. 2015;5(2):106-112.

20.	Kim J, Miller B, Siddiqui MS, Movsas B, Glide-Hurst C. FMEA of MR-Only Treatment Planning in the Pelvis. Adv Radiat Oncol. 2019;4(1):168-176.

21.	Kisling K, Johnson JL, Simonds H, et al. A risk assessment of automated treatment planning and recommendations for clinical deployment. Med Phys. 2019;46(6):2567-2574.

22.	Kricke GS, Carson MB, Lee YJ, et al. Leveraging electronic health record documentation for Failure Mode and Effects Analysis team identification. J Am Med Inform Assoc. 2017;24(2):288-294.

23.	Kunac DL, Reith DM. Identification of priorities for medication safety in neonatal intensive care. Drug Saf. 2005;28(3):251-261.

24.	Mattsson TO, Lipczak H, Pottegard A. Patient Involvement in Evaluation of Safety in Oral Antineoplastic Treatment: A Failure Mode and Effects Analysis in Patients and Health Care Professionals. Qual Manag Health Care. 2019;28(1):33-38.

25.	Manger R, Rahn D, Hoisak J, Dragojevic I. Improving the treatment planning and delivery process of Xoft electronic skin brachytherapy. Brachytherapy. 2018;17(4):702-708.

26.	Nealon KA, Balter PA, Douglas RJ, et al. Using Failure Mode and Effects Analysis to Evaluate Risk in the Clinical Adoption of Automated Contouring and Treatment Planning Tools. Pract Radiat Oncol. 2022;12(4):e344-e353.

27.	Nishioka S, Okamoto H, Chiba T, et al. Identifying risk characteristics using failure mode and effect analysis for risk management in online magnetic resonance-guided adaptive radiation therapy. Phys Imaging Radiat Oncol. 2022;23:1-7.

28.	Noel CE, Santanam L, Parikh PJ, Mutic S. Process-based quality management for clinical implementation of adaptive radiotherapy. Med Phys. 2014;41(8):081717.

29.	Rienzi L, Bariani F, Dalla Zorza M, et al. Comprehensive protocol of traceability during IVF: the result of a multicentre failure mode and effect analysis. Hum Reprod. 2017;32(8):1612-1620.

30.	Schuller BW, Burns A, Ceilley EA, et al. Failure mode and effects analysis: A community practice perspective. J Appl Clin Med Phys. 2017;18(6):258-267.

31.	Sorrentino P. Use of Failure Mode and Effects Analysis to Improve Emergency Department Handoff Processes. Clin Nurse Spec. 2016;30(1):28-37.

32.	Takemori M, Nakamura S, Sofue T, et al. Failure modes and effects analysis study for accelerator-based Boron Neutron Capture Therapy. Med Phys. 2023;50(1):424-439.

33.	Teixeira FC, de Almeida CE, Saiful Huq M. Failure mode and effects analysis based risk profile assessment for stereotactic radiosurgery programs at three cancer centers in Brazil. Med Phys. 2016;43(1):171.

34.	Walsh KE, Mazor KM, Roblin D, et al. Multisite parent-centered risk assessment to reduce pediatric oral chemotherapy errors. J Oncol Pract. 2013;9(1):e1-7.

35.	Xu AY, Bhatnagar J, Bednarz G, et al. Failure modes and effects analysis (FMEA) for Gamma Knife radiosurgery. J Appl Clin Med Phys. 2017;18(6):152-168.

36.	Xu Z, Lee S, Albani D, et al. Evaluating radiotherapy treatment delay using Failure Mode and Effects Analysis (FMEA). Radiother Oncol. 2019;137:102-109.

37.	Yarmohammadian MH, Abadi TN, Tofighi S, Esfahani SS. Performance improvement through proactive risk assessment: Using failure modes and effects analysis. J Educ Health Promot. 2014;3:28.

38.	Yousefinezhadi T, Jannesar Nobari FA, Behzadi Goodari F, Arab M. A Case Study on Improving Intensive Care Unit (ICU) Services Reliability: By Using Process Failure Mode and Effects Analysis (PFMEA). Glob J Health Sci. 2016;8(9):52635.

39.	Qaseem A, Wilt TJ, McLean RM, Forciea MA, Clinical Guidelines Committee of the American College of P. Noninvasive Treatments for Acute, Subacute, and Chronic Low Back Pain: A Clinical Practice Guideline From the American College of Physicians. Ann Intern Med. 2017;166(7):514-530.

40.	Traeger AC, Qaseem A, McAuley JH. Low Back Pain. JAMA. 2021;326(3):286.

41.	Roseen EJ, Patel KV, Ward R, et al. Trends in Chiropractic Care and Physical Rehabilitation Use Among Adults with Low Back Pain in the United States, 2002 to 2018. J Gen Intern Med. 2023.

42.	Broder-Fingert S, Stadnick NA, Hickey E, Goupil J, Diaz Lindhart Y, Feinberg E. Defining the core components of Family Navigation for autism spectrum disorder. Autism. 2020;24(2):526-530.

43.	Broder-Fingert S, Walls M, Augustyn M, et al. A hybrid type I randomized effectiveness-implementation trial of patient navigation to improve access to services for children with autism spectrum disorder. BMC Psychiatry. 2018;18(1):79.

44.	Roseen EJ, Joyce C, Winbush S, et al. Primary care barriers and facilitators to nonpharmacologic treatments for low back pain: A qualitative pilot study. PM R. 2024.